CITY OF CARMEL
GENERAL CONDITIONS FOR CONSTRUCTION CONTRACTS

ARTICLE 1 - ABBREVIATIONS AND DEFINITIONS

- Abbreviations:  The following abbreviations have the following meanings:

AA	-	Aluminum Association

AASHTO	-	American Association of State Highway & Transportation Officials

ACI	-	American Concrete Institute

AFBMA	-	Anti Friction Bearing Manufacturers Association

AGA	-	American Gas Association

AGMA	-	American Gear Manufacturers Association

AHDGA	-	American Hot Dip Galvanizer Association

AISC	-	American  Institute for Steel Construction

AISI	-	American  Iron and Steel Institute

ANSI	-	American National Standards Institute

ARI	-	American Refrigeration Institute

ASCE	-	American Society of Civil Engineers

ASHRAE	-	American Society of Heating, Refrigeration & Air Conditioning Engineers

ASME	-	American Society of Mechanical Engineers

ASTM	-	American Society of Testing and Materials

AWPI	-	American Wood Preservers Institute

AWS	-	American Welding Society

AWWA	-	American Water Works Association

CBRI	-	Copper and Brass Research Institute

CS	-	Commercial Standard (U.S. Department of Commerce)

FTI	-	Facing Title Institute Fed. Spec.

FS	-	Federal Specification (U.S.)

IEEE	-	Institute of Electrical and Electronic Engineers

IPCEA	-	Insulated Power Cable Engineers Association

MSS	-	Manufacturers Standardization Society of the Valve and Fitting Industry

NCMA	-	National Concrete Masonry Association

NEC	-	National Electric Code (U.S.)

NEMA	-	National Electrical Manufacturers Association

NFPA	-	National Fire Protection Association

NPC	-	National Plumbing Code

PS	-	United States Product Standards

SAE	-	Society of Automotive Engineers

SCPI	-	Structural Clay Products Institute

UL	-	Underwriters Laboratories

- Definitions: Wherever used and not otherwise defined in these General Conditions or in other Contract Documents, the following terms have the meanings indicated which are applicable to both the singular and plural thereof:

Addenda/Addendum - Written or graphic instruments issued prior to the opening of Bids which clarify, correct or change the Bid Documents or the Contract Documents.

Agreement -The written Agreement between Owner and Contractor covering the Work to be performed; other Contract Documents are attached to the Agreement or incorporated by reference into and made a part thereof as provided therein sometimes referred to as the “Contract”.

Application for Payment - The form prescribed or approved by Owner and accepted by the Architect/Engineer which is to be used by Contractor in requesting progress or final payments and which is to include an approved schedule of values and/or such other supporting documentation as is required by the Contract Documents, including Affidavit and Waiver of Liens.

Architect or Architect/Engineer - The person or other entity designated as Engineer by the Contract Documents.

Bid Documents - Documents required to be submitted with the Bid.

Bids - The offer or proposal of the Bidder submitted on the prescribed form setting forth the prices for the Work to be performed.

Bonds - Bid, Performance, Payment and Maintenance Bonds and other instruments of suretyship.  The term shall include letters of credit as applicable.

Change Order - A document issued on or after the Effective Date of the Agreement, recommended by the Engineer, which is signed by Contractor and Owner and which authorizes an addition, deletion or revision in the Work, or an adjustment in the Contract Price or the Contract Time.

Contract Documents - The Agreement and any exhibits thereto, Addenda (which pertain to the Contract Documents), Instructions to Bidders, Notice to Bidders, Contractor’s Bid (including documentation accompanying the Bid and any post-Bid documentation submitted prior to the Notice of Award), when attached as an exhibit to the Agreement, the Notice to Proceed, the Bonds, the General Conditions, the Additional Requirements Section, any Supplemental Conditions, the Specifications and the Drawings as the same are more specifically identified in the Agreement, together with all Amendments, Modifications, and Supplements, Change Order, Work Change Directives, Field Orders and Engineer’s written interpretations and clarifications issued pursuant to Sections 3.4 and 3.5 on or after the Effective Date of the Agreement.

Contract Price - The moneys payable by Owner to Contractor for completion of the Work in accordance with the Contract Documents as stated in the Agreement.

Contract Time - The number of days or the date stated in the Agreement for the completion of the Work.

Contractor - The person, firm or corporation with whom Owner has entered into the Agreement.

Defective - An adjective which when modifying the word Work refers to Work that is (i) unsatisfactory, faulty or deficient, in that it does not strictly conform to the requirements of the Contract Documents, (ii) does not meet the requirements of any inspection, reference standard, test or approval referred to in the Contract Documents, or (iii) has been damaged prior to Engineer’s recommendation of final payment (unless responsibility for the protection thereof has been assumed by Owner at Substantial Completion in accordance with Sections 13.10 or 13.12).

Drawings - The drawings which show the character, scope and extent of the Work to be furnished and performed by Contractor and which have been prepared or approved by Engineer and are referred to in the Contract Documents.

Effective Date of the Agreement - The date indicated in the Agreement on which it becomes effective, but if no such date is indicated, it means the date on which the Agreement is signed and delivered by the last of the two parties to sign.

Engineer - The person, firm or corporation named, employed or designated as such by the Owner to act as such and designated to observe the Work, acting directly or through duly authorized representatives.

Engineer's Consultant -A person, firm or corporation having a contract with Engineer to furnish services as Engineer's independent professional associate or consultant with respect to the Project and who is identified as such in the Special Conditions.

Field Order - A written order issued by Engineer or Owner which orders minor changes in the Work in accordance with Section 8.5 but which does not involve a change in the Contract Price or the Contract Time.

Furnish - Purchase and deliver to the work site. When used in connection with the terms "Work” or services, the term shall also mean perform.

Install - Incorporate into the Work equipment and materials furnished by others or the Contractor.

Laws and/or Regulations – Any and all applicable laws, rules, regulations, ordinances, codes, administrative actions and/or orders of any court or governmental agency or unit having jurisdiction over the Work.

Liens - Liens, charges, security interests or encumbrances upon real property or personal property.

Milestone -A principal event specified in the Contract Documents relating to an intermediate completion date or time prior to Substantial Completion of all the Work.

Notice of Award - The written notice by Owner to the apparent successful Bidder stating that upon compliance by the apparent successful Bidder with the conditions precedent enumerated therein, within the time specified, Owner will sign and deliver the Agreement.

Notice to Proceed - A written notice given by Owner to Contractor (with a copy to Engineer) fixing the date on which the Contract Time will commence to run and on which Contractor shall start to perform Contractor's obligations under the Contract Documents.

Owner - The City of Carmel, Indiana, acting by and through the agency or Department designated in the Agreement or other documents issued in solicitation of Bids; and such term shall also include the Project Manager or other duly appointed representative of such agency or department but shall not include Engineer.

Partial Utilization - The placement of a portion of the Work in service, or beneficial occupancy and use thereof, for the purpose for which it is intended (or a related purpose) before Substantial Completion of all the Work.

Project - The total construction of one or more improvements or structures of which the Work to be provided under the Contract Documents may be the whole, or a part, as indicated elsewhere in the Contract Documents.

Provide - Furnish and install.

Resident Project Representative - The authorized representative of Engineer who is assigned to the site or any part thereof.

Samples - Physical examples of materials, equipment, or workmanship that are representative of some portion of the Work and which establish the standards by which such portion of the Work will be judged.

Shop Drawings - All drawings, diagrams, illustrations, schedules and other data or information which are specifically prepared or assembled by or for Contractor, to illustrate some portion of the Work and all illustrations, diagrams and other information prepared by a Supplier and submitted by Contractor to illustrate material or equipment for some portion of the Work.

Special Conditions -The part of the Contract Documents which amends or supplements these General Conditions based on Project or Work specific requirements.

Specifications - Those portions of the Contract Documents consisting of written general or technical descriptions of materials, equipment, construction systems, standards, quality, quantity and workmanship as applied to the Work, including the performance thereof, and certain administrative details applicable thereto.

Subcontractor - An individual, firm or corporation having a direct contract with Contractor or with any other Subcontractor for the performance of a part of the Work at the site.

Substantial Completion - The stage of construction where, in the opinion of Owner, the Work (or specified portion thereof) is sufficiently complete, in accordance with the Contract Documents, so that the Work (or specified part) can be occupied, placed into service or otherwise utilized by Owner for the purpose for which it was intended.  Substantial Completion may be evidenced by a certificate thereof issued by the Engineer and signed by the Owner.

Supplier -A manufacturer, fabricator, supplier. distributor, materialman or vendor having a direct contract with Contractor or with any Subcontractor to furnish materials or equipment to be incorporated in the Work by Contractor or any Subcontractor.

Underground Facilities - All pipelines, conduits, ducts, cables, wires, manholes, vaults, tanks, tunnels or other such facilities or structures, and any encasements containing such facilities, which have been installed at or below the surface of the ground for the purpose of furnishing, storing, removing or transmitting electricity, gases, steam, liquid petroleum products, telephone or other communications, cable television, computer signals or data, sewage, drainage, traffic or other control systems, or water.

Unit Price Work - Work to be paid for on the basis of unit prices established by the Contract Documents or by Change Order as an amount stated in the Bid as a price per unit of measurement for materials, equipment or services or a scope of work as described in the Bidding Documents.

Work - The entire completed construction, or the various separately identifiable parts thereof, required to be furnished under the Contract Documents.  The Work includes and is the result and product of performing or furnishing labor and furnishing and incorporating materials and equipment into the construction, and performing or furnishing services and furnishing documents, all as required by the Contract Documents.

Work Change Directive - A written directive to Contractor, issued on or after the Effective Date of the Agreement and signed by Owner, making any change in the Work within the general scope of the Contract Documents, including but not limited to changes (i) In the Specifications (including drawings and designs), (ii) In the time, method or manner of performance of Work, (iii) in facilities, equipment, materials, services or site, and (iv) directing acceleration in the performance of the Work. A Work Change Directive will not by itself change the Contract Price or the Contract Time, but is evidence that the parties expect that the change directed or documented by a Work Change Directive will be incorporated in a subsequently issued Change Order.

Written Amendment - A written amendment of the Contract Documents, signed by Owner and Contractor on or after the Effective Date of the Agreement and normally dealing with the non-engineering or non-technical rather than strictly Work-related aspects of the Contract Documents.

ARTICLE 2 - PRELIMINARY MATTERS

2.1	Delivery of Bonds. When Contractor delivers the executed Agreement to Owner, Contractor shall also deliver to Owner such Bonds as Contractor may be required to furnish in accordance with Article 5.

2.2	Delivery of Insurance. When Contractor delivers the executed Agreement to Owner, Contractor also shall deliver to Owner, with a copy to Engineer, certificates of Insurance (and other evidence thereof as requested by Owner) which Contractor is required to purchase and maintain in accordance with Article 5, and Owner shall deliver to Contractor certificates (and other evidence of insurance requested by Contractor) which, is required to purchase and maintain in accordance with Article 5.

2.3	Copies of Documents. Unless otherwise specified, Owner shall furnish to Contractor five (5) copies of the Contract Documents, or as many copies as are available from the printings made for bidding purposes and as are reasonably necessary for the execution of the Work.  Additional copies will be furnished, upon request, at the cost of reproduction.

2.4	Commencement of Contract Times Notice to Proceed.  Subsequent to or concurrently with the execution of the Agreement, Owner shall give Contractor a written Notice to Proceed specifying the date on which Contractor shall commence the Work. The date designated in the Notice to Proceed shall be the date on which the Contract Time will commence to run.

2.5	Starting the Work.  Contractor shall start to perform the Work on the date designated In the Notice to Proceed, but no Work shall be done at the site prior to the date of the Notice to Proceed.

2.6	Before Starting Construction.  Before undertaking each part of the Work, Contractor shall carefully study and compare the Contract Documents and check and verify pertinent figures, standards, quantities, materials, field measurements, access, and other requirements or conditions affecting the work, Contractor shall promptly report in writing to Engineer any conflict, error, discrepancy or other adverse condition or circumstance which Contractor may discover, and shall obtain a written interpretation or clarification from Engineer before proceeding with any Work affected thereby.  Contractor shall assume all risks and bear all costs associated with any conflicts, errors, ambiguities, discrepancies or conditions which are not discovered due to his failure to conduct such study and comparison, or which are discovered but not reported as required by this Section.

2.7	Initial Schedule and Submissions.  Within ten (10) days after the Effective Date of the Agreement Contractor shall submit to Engineer for review:

2.7.1	A proposed progress schedule indicating the starting and completion dates of the various stages of the Work to be performed under this Contract. This schedule shall be in the form of an Arrow Diagram and shall reflect the Contract completion date.  Engineer will review the proposed progress schedule to determine conformity to the Contract Documents.  During the course of performing the Work, Contractor shall, at least monthly, submit to Engineer a revised progress schedule indicating any anticipated change from the original or previously revised progress schedule.  The revised schedule shall include provisions for performing Work authorized under approved Change Orders.  Engineer will review the original and revised progress schedules for general conformity with the Contract Documents and will make recommendations to the Owner concerning approval thereof; however the review, approval or other action taken by Engineer or Owner in respect of such schedules shall not relieve the Contractor of it’s obligations to perform the Work within the Contract Time.  If Contractor shall fail to adhere to the approved original or revised progress schedule, except when due to Excusable Delays for which a claim has been submitted by Contractor and approved by Owner, he shall promptly adopt such other or additional means and methods of construction and commit such additional manpower, equipment and other resources as necessary to make up for the time lost and to assure completion of the Work in accordance with the Contract Documents.

2.7.2	A preliminary submittal schedule showing proposed dates for submission of required Shop Drawings, Samples and product data.  Such schedule shall also include such durations as prescribed by Engineer to account for anticipated time allotments for review, approval or other action upon submittals by Engineer and additional allowances for resubmittals by Contractor; and

2.7.3	A preliminary schedule of values for all of the Work which will include quantities and prices of items aggregating the Contract Price and will subdivide the Work into component parts in sufficient detail to serve as the basis for progress payments during construction.  Such prices will include an appropriate amount of overhead and profit applicable to each Item of Work, which will be confirmed in writing by Contractor at the time of submission.

2.7.3.1	Mobilization for Contractor and any tier of subcontractor(s) shall be considered collectively and shall not exceed 10 percent (10%) of the Contract Price.  Mobilization shall be those costs associated with the initiation of the Project and sitework, including but not limited to, transporting of personnel, equipment, materials, supplies, incidental items; establishment of the field offices, temporary facilities necessary for the project, bonds and insurances, submittal requirements, permits, field supervision, final cleanup and demobilization.  Mobilization does not include such items as, contract negotiations and bid preparation.  Where the Work is covered by Unit Price and no item has been included for mobilization, then this Work is considered incidental to the Work and will not be paid separately.

2.7.3.2.	Where the work is covered by Unit Prices, and item(s) for mobilization, as described in 2.7.3.1 have been included, the maximum allowable amount shall be ten percent (10%) of the aggregate of all items excluding mobilization.  Where mobilization is included in multiple items, then the aggregate amount of all mobilization items shall not exceed the allowable ten percent (10%).

2.7.3.3	Costs for submittal requirements, field office and supervision, where identified separately in the schedule of values shall be considered for payment monthly.  When the cost is a lump sum as submitted in accordance with 2.7.3, the monthly cost shall be established by dividing the lump sum by the number of monthly estimates based on the original Contract Time.  No adjustments shall be made for any Contract Time extensions.

2.7.3.4	Mobilization shall be included in the progress payments, in accordance with the schedule of values and Unit Prices.  When the Work, excluding mobilization and inventory, has progressed to an amount equal to five percent (5%) or more of the Contract Price, then an amount of not more than fifty percent (50%) of the mobilization cost will be considered for inclusion in the progress payment.  Prior to the established five percent (5%), Owner may consider payment on invoices for bonds and insurances and permits; this amount shall be subtracted from the total amount for mobilization. Not more than forty percent (40%) of the mobilization cost will be considered for inclusion in the progress payments once the Work, excluding mobilization and inventory, has progressed to an amount equal to fifty percent (50%) of the Contract Price.  The remaining mobilization payment will be paid as part of the final payment.

2.7.4	Where the Work is covered by Unit Prices and there have been included lump sum items, the Contractor shall submit to Engineer a schedule of values in accordance with the paragraph 2.7.3 for those lump sum items.

2.8	Preconstruction Conference.  Before Contractor starts the Work at the site, a conference attended by Contractor, Owner, Engineer, and others as appropriate will be held to discuss the schedules referred to in Section 2.7, to discuss procedures for handling Shop Drawings and other submittals and for processing Applications for Payment, and to establish other procedures and understandings bearing upon coordination and performance of the Work.

2.9	Finalizing Schedules. Unless otherwise provided in the Contract Documents, at least ten (10) days before submission of the first Application for Payment, a conference attended by Contractor, Engineer, and others as appropriate, will be held to finalize the schedules submitted in accordance with Section 2.7.

2.9.1 	Contractor shall have an additional ten (10) days to make corrections and adjustments and to complete and resubmit the schedules. No progress Payment shall be made to Contractor until the schedules are submitted to and acceptable to Engineer as provided below.

2.9.2	The finalized progress schedule will be acceptable to Engineer as providing an orderly progression of the Work to completion within any specified Milestones and the Contract Times, but such acceptance will neither impose on Engineer responsibility for the sequencing, scheduling or progress of the Work nor interfere with or relieve Contractor from Contractor's full responsibility therefor.

2.9.3	Contractor's schedule of Shop Drawing and Sample submissions will be acceptable to Engineer as providing a workable arrangement for reviewing and processing the required submittals.

2.9.4	Contractor's schedule of values will be acceptable to Engineer as to form and substance.

ARTICLE 3 - CONTRACT DOCUMENTS

3.1	Integration of Contract Documents.  The Contract Documents comprise the entire Agreement between Owner and Contractor concerning the Work.  The Contract Documents are complementary; what is called for by one is as binding as if called for by all.  The Contract Documents will be construed in accordance with the law of the State of Indiana and without regard to the party by or for whom they were prepared or drafted.

3.2	Intent and Meaning. It is the intent of the Contract Documents to describe a functionally complete Project (or part thereof) to be constructed in accordance therewith.  Any Work, materials or equipment that may reasonably be inferred from the Contract Documents, as being required to produce the intended result will be supplied whether or not specifically called for.  Notations, details or other descriptions, which apply to one of a number of situations, materials, processes or Work items, shall apply to all except as specifically stated otherwise.  When words which have a well-known technical or trade meaning are used to describe Work, materials or equipment, such words shall be given that meaning unless a different meaning is reasonably apparent as determined by the Engineer.  Reference to standard specifications, manuals or codes of any technical society, organization or association, or to the Laws or Regulations of any governmental authority, whether such reference be specific or by implication, shall mean the latest standard specification, manual or code or Laws or Regulations in effect at the time of opening of Bids.  If said standard specification, manual or code or Laws or Regulations are promulgated, amended, revised or otherwise changed subsequent to the opening of Bids, Contractor shall notify Owner who may direct compliance under Section 9.1. However, no provision of any referenced standard specification, manual or code (whether or not specifically incorporated by reference in the Contract Documents) shall be effective to change the duties and responsibilities of Owner, Contractor or Engineer, or any of their consultants, agents or employees, or to limit or impair any right or remedy of the Owner, as set forth in the Contract Documents, nor shall it be effective to assign to the Owner, Engineer or any of their respective consultants, agents or employees any duty or authority to supervise or direct the furnishing or performance of the Work or any duty or authority to undertake responsibility, contrary to the provisions of Section 8.10 or 8.11.

3.3	Duty To Report Discrepancies. If, during the performance of the Work, Contractor discovers a conflict, error or discrepancy in the Contract Documents, Contractor shall so report to Engineer in writing at once and before proceeding with the Work affected thereby and shall obtain a written interpretation or clarification from Engineer.

3.4	Major Modification.  The Contract Documents may be amended to provide for additions, deletions and revisions in the Work or to modify the terms and conditions thereof by (i) a formal Written Amendment, or (ii) a Change Order (pursuant to Section 9.4) or (iii) a Work Change Directive (pursuant to Section 9.1). As indicated in Sections 10.2 and 11.5, the Contract Price and Contract Time may only be changed by a Change Order or a Written Amendment.

3.5	Minor Deviations. The requirements of the Contract Documents may be supplemented, and minor variations and deviations in the Work may be authorized by (i) a Field Order (pursuant to Section 8.5), or (ii) an Engineer’s approval of a Shop Drawing, Working Drawing, or Samples (pursuant to Section 6.22) or an Engineer’s written interpretation or clarification (pursuant to Section 8.4).

3.6	Reuse of Documents.  Neither Contractor nor any Subcontractor or Supplier or other person or organization performing or furnishing any of the Work under a direct or indirect contract with Owner shall have or acquire any title to or ownership rights in any of the Drawings, Specifications or other documents (or copies of any thereof) prepared by or bearing the seal of Engineer; and they shall not reuse any of them on extensions of the Project or any other project without written consent of Owner and Engineer and specific written verification or adaptation by Engineer.

ARTICLE 4 - AVAILABILITY OF LANDS; PHYSICAL CONDITIONS

4.1	Availability of Lands.  Owner shall furnish, as indicated in the Contract Documents, the lands upon which the Work is to be performed, rights-of-way and easements for access thereto, and such other lands which are designated for the use of Contractor.  Owner shall identify any encumbrances or restrictions not of general application but specifically related to use of lands so furnished with which Contractor will have to comply in performing the Work.  Easements for permanent structures or permanent changes in existing facilities will be obtained and paid for by Owner, unless otherwise provided in the Contract Documents. If Contractor believes that any delay in Owner furnishing these lands, rights-of-way or easements entitles Contractor to an extension of the Contract Time, Contractor may make a claim therefore as provided in Article 11.  Contractor shall provide for all additional lands and access thereto that may be required for temporary construction facilities or storage of materials and equipment.

4.1.1	The Owner shall provide permanent easements and temporary construction easements as shown on the Drawings for buried pipelines across private property. If the easements obtained are not sufficient for the Work, the Contractor shall obtain any additional easements required. There will be no additional compensation made for obtaining these easements, damages to private property outside easements, or additional cost to the Contractor because of the easements or lack thereof.

4.2	Subsurface and Physical Conditions (Excluding Underground Facilities). Reports of explorations and tests of subsurface conditions and drawings of physical conditions in or relating to existing surface or subsurface structures at or contiguous to the site (except Underground Facilities) have been utilized and relied upon by Engineer in preparing the Contract Documents.  Contractor may rely upon the general accuracy of the “technical data” contained in such reports and drawings but such reports and drawings are not Contract Documents.  Such "technical data” is identified in the Specifications.  Except for reliance on such “technical data”, Contractor may not rely upon and may not make any claim against Owner, Engineer or any of Engineer's Consultants with respect to (i) the completeness of such reports and drawings for Contractor’s purposes, including, but not limited to, any aspects of the means, methods, techniques, sequences and procedures of construction to be employed by Contractor and safety precautions and programs incident thereto, or (ii) other data, interpretations, opinions and information contained in such reports or shown or indicated in such drawings.

4.3	Differing Subsurface or Physical Conditions. If Contractor uncovers, observes or otherwise becomes aware of any subsurface or physical condition (other than Underground Facilities) at or contiguous to the site and believes that such condition either (i) differs materially from that shown or indicated in the Contract Documents, (ii) is of an unusual nature, and differs materially from conditions ordinarily encountered and generally recognized as inherent in work of the character provided for in the Contract Documents, or (iii) is of such a nature as to establish that any "technical data" on which Contractor is entitled to rely as provided in paragraph 4.2 is materially inaccurate; then Contractor shall, immediately upon becoming aware thereof and before further disturbing or taking other action in respect thereof or performing any Work in connection therewith (except in an emergency as permitted by Section 6.21), notify Owner and Engineer in writing about such condition, which notice shall state the Contractor’s recommendations or proposals for taking action in connection with the conditions.

4.3.1	Contractor shall not further disturb such conditions or perform any Work in connection therewith (except as aforesaid) until receipt of a written directive from Owner or Engineer to do so, but to the fullest extent possible Contractor shall continue to prosecute all other Work not affected by the conditions;

4.3.2	Engineer will promptly review the pertinent conditions, determine the necessity of obtaining additional explorations or tests with respect thereto and advise Owner in writing (with a copy to Contractor) of Engineer's findings and conclusions;

4.3.3	If Owner in consultation with the Engineer concludes that a change in the Contract Documents or other action is required because of the conditions, a Work Change Directive or other instructions or interpretations may be issued as provided in Article 9 to reflect and document the consequences of the conditions;

4.3.4	In each such case, an increase or decrease in the Contract Price or an extension or shortening of the Contract Time, or any combination thereof, may be allowable, but only to the extent that (i) evidence of such conditions could not with the exercise of reasonable competence and diligence have been discovered or foreseen by Contractor prior to submission of the Contractor’s Bid, (ii) the Contractor, by the terms of the Contract Documents, has not assumed the risk of such conditions, and (iii) Contractor has explicitly fulfilled the written notice requirements provided by this Section 4.3. The Contractor shall in no event be entitled to an increase in the Contract Price in excess of direct costs to perform authorized additional or changed Work to address the conditions, without additional allowances for delays or suspension of Work.  If Owner and Contractor are unable to agree as to the amount or length of the adjustment to the Contract Price or Time, a claim may be made there for as provided in Articles 10 and 11.  However, Owner and Engineer shall not be liable to Contractor for any incidental or consequential damages, claims or costs including, but not limited to, costs, losses or damages incurred or sustained by Contractor on or in connection with any other project or anticipated project or home office overhead.

4.4	Underground Facilities.

4.4.1	Shown or Indicated: The information and data shown or indicated in the Contract Documents with respect to existing Underground Facilities at or contiguous to the site is based on information and data furnished to Owner or Engineer by the owners of such Underground Facilities or by others.  Owner and Engineer shall not be responsible for the accuracy or completeness of any such information or data.  Contractor shall have the sole responsibility for reviewing and checking all such information and data, for locating all Underground Facilities, shown or indicated in the Contract Documents, for coordination of the Work with the owners of such Underground Facilities during construction, for the safety and protection thereof as provided in Section 6.20 and for repairing any damage thereto resulting from the Work or Contractor's operations, the cost of all of which having been included in the Contract Price.

4.4.2	Not Shown or Indicated. If an Underground Facility is uncovered or revealed at or contiguous to the site which was not shown or indicated in the Contract Documents and of which Contractor could not reasonably have been expected to be aware, Contractor shall promptly after becoming aware thereof and before further disturbing conditions affected thereby (except in an emergency as permitted by Paragraph 6.21), notify the owner of such Underground Facility and give written notice thereof to that owner and to Owner and Engineer.  Engineer will promptly review the Underground Facility to determine the extent to which the Contract Documents should be modified to reflect and document the consequences of the existence of the Underground Facility, and the Contract Documents will be amended or supplemented to the extent necessary.  During such time, Contractor shall be allowed an extension of the Contract Time, provided such delay affects the critical path, or both, to the extent that they are attributable to the existence of any Underground Facility that was not shown or indicated in the Contract Documents and of which Contractor could not reasonably have been expected to be aware.  If the parties are unable to agree as to the amount or length thereof, Contractor may make a claim therefore as provided in Articles 10 and 11.  However, Owner and Engineer shall not be liable to Contractor for any incidental or consequential damages, claims or costs, including but not limited to, losses or damages incurred or sustained by Contractor on or in connection with any other project or anticipated project, home office overhead, or for any claims, costs, losses or damages caused by or arising from any assessment, penalty or other liability imposed upon Contractor by utility companies or third parties.

4.5	Reference Points and Layout.  Owner or other parties will provide engineering surveys for construction to establish reference points for construction as determined by Engineer to be necessary to enable Contractor to proceed with the Work unless otherwise specified. Contractor shall be responsible for laying out the Work, shall locate all mechanical and electrical services uncovered by excavation, shall establish all grades, lines, levels and bench-marks, and shall protect and preserve the established reference points and shall make no changes or relocations without the prior written approval of Owner.  Contractor shall report to Engineer when any reference point is lost or destroyed or requires relocation because of necessary changes in grades or locations, and shall be responsible for the accurate replacement or relocation of such reference points by professionally qualified personnel.  Contractor shall maintain a bound surveyor's field notebook to accurately record all discrepancies, if any, discovered in Owner’s data.  The field notebook shall be furnished to and become the property of Owner upon completion of the Work.

4.6	Lines and Grades.

4.6.1	All work under this Contract shall be constructed in accordance with the lines and grades shown on the Plans, or as given by Engineer.  The full responsibility for keeping alignment and grade shall rest upon Contractor.  Contractor shall establish base line controlling points.  Reference marks for lines and grades shall be set by Contractor as the Work progresses and will be located to cause as little inconvenience to the prosecution of the Work as possible. Contractor shall place excavation and other materials so as to cause no inconvenience in the use of the reference marks provided.  Contractor shall remove any obstructions placed by Contractor contrary to this provision at no cost to Owner.

4.6.2	Contractor shall furnish and maintain, at his own expense, stakes and other such materials, and give such assistance, including qualified helpers, as may be required by Engineer for setting and checking line and grade reference marks.  Contractor shall check such reference marks by such means as he may deem necessary and, before using the reference marks, shall call Engineer’s attention to any inaccuracies.  Contractor shall, at his own expense, establish all working or construction lines and grades as required from the reference marks set by Engineer, and shall be solely responsible for the accuracy thereof.  Contractor shall, however, be subject to the check and review of Engineer.  Contractor shall keep Engineer informed a reasonable time in advance as to his need for line and grade reference marks, in order that they may be furnished and all necessary measurements made for record and payment with the minimum of inconvenience to Engineer or of delay to Contractor.  When necessary, working operations shall be suspended for such reasonable time as Engineer may require for this purpose.

4.6.3	Contractor shall safeguard all points, stakes, grade marks, monuments and beach-marks made or established on the Work, bear the cost of reestablishing them if disturbed, and bear the entire expense of rectifying work improperly installed due to not maintaining or protecting or to removing without authorization such established points, stakes and marks.  Contractor shall safeguard all existing and known property corners, monuments and marks adjacent to but not related to the Work and, if required, shall bear the cost of reestablishing them if disturbed or destroyed.

4.6.4	All elevations indicated or specified refer to the Mean Sea Level Datum Plane, 1929 General Adjustment, of the United States Coast and Geodetic Survey and are expressed in feet and decimal parts thereof, or in feet and inches.

4.7	Hazardous Materials.

4.7.1	For the purpose of this section, “Hazardous Material” means any hazardous, special, radioactive or toxic substance, material or waste which is or becomes regulated by any local government authority, the State of Indiana or the United States Government.  The term “hazardous material” includes, without limitation, any material or substance which is (i) defined as a “hazardous substance” under I.C. 13-7-8.7-1 of the Indiana Hazardous Substance Response Trust Fund Act, (ii) petroleum, (iii) asbestos, (iv) designated as a hazardous substance pursuant to the Federal Water Pollution Control Act (33 U.S.C. § 1251 et. seq.), (v) defined as a “hazardous waste” pursuant to the Federal Resource Conservation and Recovery Act (42 U.S.C. § 6901 et seq.), (vi) defined as a “hazardous substance” pursuant to the Comprehensive Environmental Response, Compensation and Liability Act (42 U.S.C. § 9601 et seq., (vii) defined as a “regulated substance” pursuant to the Solid Waste Disposal Act (42 U.S.C. § 6991 et seq.), (viii) defined as a toxic “chemical substance” pursuant to the Toxic Substance Control Act (7 U.S.C. § 136 et seq.), (ix) defined as a "hazardous chemical" or "hazardous substance" pursuant to the Emergency Planning and Community Right to Know Act (42 U.S.C. § 11001 et seq.) or (x) defined as a “radioactive waste” pursuant to the Atomic Energy Act (42 U.S.C. § 2011 et seq.)

4.7.2	Owner shall be responsible for the existence of any Hazardous Materials uncovered or revealed at the site, which were not shown or indicated in Drawings or Specifications or identified in the Contract Documents to be within the scope of the Work.  Owner shall not be responsible for any such materials brought to the site by Contractor, Subcontractor, Supplier or anyone else for whom Contractor is responsible.

4.7.3	Contractor shall be the party responsible for reporting to the appropriate agencies and authorities any release or discharge of any Hazardous Materials.

4.7.4 	Upon encountering any Hazardous Materials Contractor shall immediately (i) stop all Work in connection with such Hazardous Materials and in any area affected thereby (except in an emergency as required by Section 6.21), (ii) notify the appropriate agencies or authorities, (iii) notify Owner and Engineer (and thereafter confirm such notice in writing), (iv) establish site security by excluding unnecessary traffic and personnel from the affected area, (v) conduct operations within the affected area to minimize exposure to personnel and the general public and to eliminate the potential for airborne dispersion, and (vi) as necessary to carry out the requirements of this section, handle, store and/or dispose of Hazardous Materials in a proper manner.

4.7.5	Contractor shall remain responsible for the jobsite until Owner has been notified of the uncovering or revealing of Hazardous Materials and Owner has assumed formal control of the worksite from Contractor.

4.7.6	After completing the above obligations, Contractor shall be required to resume Work in connection with such Hazardous Materials, if directed by Owner, after Owner has obtained any required permits related thereto and established any special terms or conditions under which said Work shall be performed.

4.7.7	Contractor claims qualifying under this section are intended to be treated as differing site condition claims and therefore the provisions of Sections 4.2 and 4.3 apply.

ARTICLE 5 – BONDS, INSURANCE AND INDEMNIFICATION.

5.1	Performance, Payment and Other Bonds. Contractor shall furnish Performance and Payment Bonds, each in an amount at least equal to one hundred percent (100%) of the Contract Price as security for the faithful performance and payment of all Contractor’s obligations under the Contract Documents.  These Bonds shall remain in effect at least until one (1) year after final payment and settlement with the Contractor and as provided otherwise by Law or Regulation or by the Contract Documents.  All Bonds shall be in the forms prescribed by Law, Regulation, and the Contract Documents and be executed by such Sureties as (i) are licensed to conduct business in the State of Indiana, and (ii) are named in the current list of “Companies Holding Certificates of Authority as Acceptable Sureties on Federal Bonds and as Acceptable Reinsuring Companies” as published in Circular 570 (amended) by the Audit Staff Bureau of Government Financial Operations, U.S. Treasury Department.  All Bonds signed by an agent must be accompanied by a certified copy of the power of attorney or other instrument establishing the such agent's authority to act.

5.2	Maintenance Bond. Contractor shall, as a condition to Owner’s obligation to make final payment, supply a three (3) year Maintenance Bond executed by a surety meeting the qualifications set forth in the preceding Section and in such form as prescribed by the Contract Documents, which bond shall secure the obligations contained in Section 12.7, beginning on the date of Final Acceptance in an amount equal to ten percent (10%) of the Contract Price as adjusted for Change Orders or such different percentage as may be specified by other Contract Documents.

5.3	Additional Requirements.

5.3.1	Substitute Bonds. If the Surety on any Bond furnished by Contractor becomes a party to a supervision, liquidation, rehabilitation or other similar action, or if its right or lawful authority to do business in the State of Indiana is terminated, Contractor shall, within ten (10) days thereafter substitute another Bond and Surety, both of which must be acceptable to Owner.  Failure of Contractor to obtain a substitute Bond shall constitute a material breach of Contract and may at the option of Owner result in the termination of the Contract upon the ground of Contractor’s default.

## 5.3.2  Licensed Sureties and Insurers.  All Bonds and Insurance required by the Contract Documents to be purchased and maintained by Owner or Contractor shall be obtained, from surety or insurance companies that are duly licensed or authorized in the jurisdiction in which the Project is located to issue Bonds or insurance policies for the limits and coverages so required.  Such surety and insurance companies shall also meet such additional requirements and qualifications as may be provided in the Special Conditions, if any.  The surety and insurance companies providing any coverages on this Project shall have and maintain during the term of this Agreement a minimum A.M. Best (Best's Key Rating Guide) rating classification of "A-".

## 5.3.3  Certificates of Insurance.  Contractor shall deliver to Owner, with copies to each Additional Insured identified in the Contract Documents and Special Conditions, if any, certificates of insurance (and other evidence of insurance requested by Owner or any other additional insured) which Contractor is required to purchase and maintain in accordance with paragraph 5.4.  The Contractor shall file policies and/or certificates of insurance, in duplicate, for all coverages required with the Owner and the Engineer, naming the Owner and the Engineer as Certificate Holders. Addresses of Owner and Engineer must also be shown.  The certificate of insurance shall show that all coverages are provided on an occurrence basis and shall indicate the aggregate limit available for this Project as of the date the certificate is issued. Binders will be accepted as evidence of coverage for only the first ninety (90) days and cannot be renewed or extended beyond that time.  All insurance policies and certificates of insurance must include a provision stating a minimum thirty (30) days' prior written notice will be provided to the Owner and Engineer for any cancellation, non-renewal, material change, or reduction of coverage. The Contractor shall cease operations upon the occurrence of any such cancellation, non-renewal, material change, or reduction of coverage, and shall not resume operations until satisfactory replacement insurance is provided, coverage is effective and certificates of insurance are received.

5.4	Contractor’s Liability Insurance.  Contractor shall purchase and maintain such commercial general liability and other insurance as is required for the Work being performed and furnished and as will protect Contractor, Owner and Engineer, their employees, officers, or agents from (i) claims under workers' or workmen's compensation, disability benefits and other similar employee benefit acts which are applicable to the Work to be performed including private entities performing Work at the site and exempt from the coverage on account of number of employees or occupation, which entities shall maintain voluntary compensation coverage at the same limits specified for the mandatory coverage for the duration of the Project; in case any such Work is sublet, the Contractor shall require the Subcontractor to provide insurance for all employees of the Subcontractor engaged in such Work unless such employees are covered by the coverage afforded by the Contractor's insurance; (ii) claims for damages because of bodily injury, occupational sickness or disease, or death of Contractor’s employees or persons or entities excluded by statute from the requirements of (i), but required by the Contract Documents to provide the insurance required therein; (iii) claims for damages because of bodily injury, sickness or disease, or death of any person other than Contractor’s employees; (iv) claims for damages insured by personal injury liability coverage which are sustained by any person as a result of an offense directly or indirectly related to the employment of such person by Contractor, or by any other person for any other reason; (v) claims for damages, other than to the Work itself, because of physical injury to or destruction of tangible property wherever located, including loss of use resulting there from; (vi) claims for bodily injury or property damage arising out of completed operations; and (vii) claims involving contractual liability insurance applicable to the Contractor's obligations under the Indemnification requirements of Section 5.11.

i.	Contractor shall purchase and maintain commercial general liability and commercial automobile liability insurance during the entire term of this Agreement. The policies shall be based on terms commonly referred to in the insurance industry as an occurrence coverage form (Claims made policy forms are not acceptable.)

ii.	The certificate of insurance for commercial general liability insurance shall indicate the amount of the aggregate limit remaining for this Project as of the date of the certificate.

iii.	The commercial general liability policy must contain the following definition of "insured contract":

"That part of any other contract or agreement pertaining to your business (including an indemnification of a municipality in connection with work performed for a municipality) under which you assume the tort liability of another party to pay for "bodily injury" or "property damage" to a third person or organization.  Tort liability means a liability that would be imposed by law in the absence of any contract or agreement."

iv.	The certificate of insurance shall include this specific language on the certificate of insurance confirming this definition of an insured contract or a certified copy of the policy is to be submitted which includes this definition of an insured contract.

v.	The Contractor shall purchase and maintain commercial automobile liability coverages for any owned or leased vehicles. Non-owned and hired auto liability coverages shall also be included.

vi.	This policy shall cover the total Project and include explosion, collapse, and underground coverages for the entire Work provided by the Contractor and Subcontractors.

vii.	The policy shall stipulate that the "designated Contractor” includes the Contractor and all Sub-contractors engaged in the Work.

viii.	The original policy shall be submitted to and filed with the Owner or its designated representative.

5.4.1	The insurance required by this Section shall be written for not less than the minimum limits of liability and coverages as provided herein or as required by Law, or by the Special Conditions, whichever is greater.  The Commercial General Liability Insurance shall include coverage of (i) premises and operations, (ii) Contractual liability as applicable to any indemnification hold harmless agreements in the Contract Documents, (iii) Products and Completed Operations, with completed operations coverage being maintained for a period of one (1) year after final payment and Contractor shall continue to provide evidence of such coverage to Owner during the aforementioned period, (iv) Broad form Property Damage - including completed operations, (v) Fellow Employee claims under Personal Injury; and (vi) Independent contractors.  Such insurance shall specifically include coverage for property damage from explosion, collapse, and underground operations.  Coverage for explosion, collapse, and underground operations shall include blasting or explosion, collapse of structures or structural injury due to grading of land, excavation, filling, back filling, tunneling, pile driving, caisson work, moving, shoring, underpinning, raising of or demolition of any structure, or removal or rebuilding of any structural support of a building or structure.  Such insurance shall further include coverage for damage to wires, conduits, pipes, mains, sewers, or other similar apparatus encountered below the surface of the ground when such damage is caused by any occurrence arising out of the performance of the Work, performed by Contractor or by any Subcontractor or anyone directly or indirectly employed by either.

5.4.2	The minimum limits of liability for all coverages in each of the proceeding paragraphs above shall be as follows, unless otherwise specifically required by Law or by the Special Conditions (whichever is greater).  Coverages shall be maintained without interruption from the date of commencement of the Work until date of final payment and termination of any coverage required to be maintained after final payment.

### A.  Workers Compensation/Employer’s Liability:

Coverage A (Worker’s Compensation) - Statutory

Coverage B (Employer’s Liability) - $1,000,000 / each accident; $1,000,000 Disease-each employee; $1,000,000 Disease-policy limit.

This coverage to be valid in all states covered for the Contract Work.

### B.  Commercial General Liability:

General Aggregate (except Products/Completed Operations) - $6,000,000;

Bodily Injury & Property Damage - $5,000,000 Combined Single Limit/Per Occurrence;

Personal/Advertising Injury $5,000,000/occurrence;

Products/Completed Operations General Aggregate - $5,000,000;

Coverage to include exposures listed in 5.4.2.2;

Coverage includes Contractual Liability and Broad Form Property Damage including Completed Operations;

Coverage to apply on a “Per Project” basis in order that coverage will not be diminished by unrelated work.

### C. Commercial Automobile Liability (Owned, Leased, Hired/Non-Owned):

Bodily Injury & Property Damage - $5,000,000 / occurrence.

All coverages provided above shall be endorsed to include the Owner, Engineer as Additional Insured except for A (Worker’s Compensation) and will stipulate that this coverage is primary respecting any other coverages the Owner, Engineer or Consultants might have.  The additional insured endorsement will include “Completed Operations” of the Contractor (and any Subcontractor).  The coverage requirements apply to all Contractor’s, Subcontractors, Sub-subcontractors and Suppliers; Contractor is responsible to verify these requirements for each and every one of its Subcontractors, Sub-subcontractors and Suppliers.

5.4.3	If a commercial umbrella liability policy is used to satisfy the minimum limits of liability requirements, the combined limits must equal these minimum limits of liability.

5.4.4 If the aggregate liability limits required by this Agreement for any policy subsequently fall below the aggregate limits required by this Agreement for this Project, immediate steps shall be taken to effect reinstatement of the minimum aggregate liability limits required by this Agreement. A revised certificate of insurance, in compliance with paragraph 5.3.3, is required to confirm compliance with this requirement.  Any additional premiums resulting from such reinstatement shall be at no additional cost to Owner.

5.4.5	Upon specific request by Owner or Engineer, the original policy shall be filed with the Owner or his designated representative within thirty (30) days of request.

5.4.6	With respect to products and/or completed operations insurance coverage, will remain in effect for at least three (3) years after final payment (and Contractor shall furnish Owner, and each other insured identified in the General Conditions to whom a certificate of insurance has been issued, evidence satisfactory to Owner and any such other insured or additional insured of continuation of such insurance at final payment and three (3) year thereafter).

5.4.7	These coverage requirements and minimum coverage limits are to provide the minimum acceptable insurance coverages and their existence does not in any way limit or reduce the Contractor's or Subcontractor's indemnity obligations under the Contract Documents.

5.4.8	No representation or warranty is made by the Owner or Engineer regarding the sufficiency or adequacy of the insurance requirements, coverages or limits stated in the Contract Documents. The Contractor and Subcontractors are advised to consult with their respective insurance agents or professional advisors to determine their coverage needs and requirements.

5.4.9	Contractor shall be responsible for paying all deductible amounts.

5.5	Owner’s Liability Insurance.  In addition to the insurance required in Section 5.4 by Contractor, Owner, at Owner’s option, may procure and maintain Owner's own liability insurance as will, in Owner’s opinion, protect Owner from any contingent liability to others or damages because of bodily injury, including death and property damage, which may arise from operations under this Agreement.

5.6	Property Insurance.  Owner shall purchase and maintain property insurance / builder’s risk insurance upon the Work at the site of the Project in the amount of the full replacement cost thereof, except for the errors and omissions of the Engineer.

5.6.1	The Owner shall purchase and maintain special form coverage and include demolition occasioned by enforcement of Laws and Regulations; earthquake; water damage; and such other perils as may be specifically required by the General Conditions Builders Risk Property Insurance upon the Work at the site to the full insurable replacement cost value thereof, including underground pipelines. The Owner shall also purchase and maintain special form coverage and include demolition occasioned by enforcement of Laws and Regulations; earthquake; water damage; and such other perils as may be specifically required by the General Conditions on any property, whether real property or personal property, whether or not it is located at the site or in transit, in which the Owner and/or Engineer have an insurable interest as evidenced by current Estimates, or other terms of this Agreement, and include the interests of Owner, Contractor, Subcontractors of any tier, Engineer, Engineer's Consultants and any other persons or entities identified in the General Conditions, each of whom is deemed to have an insurable interest and shall be listed as an additional insured.

5.6.2	This coverage is to be provided on a separate Builder's Risk completed value policy, with special form coverage. This insurance shall:

5.6.2.1	include expense incurred in the repair or replacement of any insured property (including, but not limited to, fees and charges of Engineers and architects);

5.6.2.2 	cover materials, property, and equipment in transit for incorporation in the Work or stored at the site or at another location prior to being incorporated in the Work;

5.6.2.3 	be maintained in effect until final payment and settlement is made unless otherwise agreed to in writing by Owner, Contractor, and Engineer with thirty (30) days written notice to each other additional insured to whom a certificate of insurance has been issued prior to the cessation of such coverage.

5.6.3 	Owner shall purchase and maintain such boiler and machinery insurance or additional property insurance as may be required by the Special Conditions or Laws and Regulations which will include the interests of Owner. Contractor, Subcontractors, Engineer, Engineer's Consultants and any other persons or entities identified in the Special Conditions each of whom is deemed to have an insurable interest and shall be listed as an insured or additional insured.

5.7	Waiver of Subrogation.

5.7.1. Owner and Contractor intend that all policies purchased in accordance with paragraphs 5.6 will protect Owner, Contractor, Subcontractors and Engineer and all other persons or entities identified in the General Conditions to be listed as insureds or additional insureds in such policies and will provide primary coverage for all losses and damages caused by the perils covered thereby. All such policies shall contain provisions to the effect that in the event of payment of any loss or damage, the insurers will have no rights of recovery against any of the insureds or additional insureds thereunder. Owner and Contractor waive all rights against each other and their respective officers, directors, employees, and agents for all losses and damages caused by, arising out of, or resulting from any of the perils covered by such policies and any other property insurance applicable to the Work; and, in addition, waive all such rights against Subcontractors and Engineer and all other persons or entities identified in the General Conditions to be listed as insureds or additional insureds under such policies for losses and damages so caused. None of the above waivers shall extend to the rights that any party making such a waiver may have to the proceeds of insurance held by Contractor as trustee or otherwise payable under any policy so issued. The property insurance policies shall be modified to reflect and approve this waiver of subrogation rights. However, this waiver shall not apply to losses arising out of errors or omissions of the Engineer, Engineer’s Consultants or Sub-Consultants, that are not covered by the Builder’s Risk policy.

5.8	Acceptance of Insurance.  If Owner has any objection to the coverage afforded by or other provisions of the Insurance required to be purchased and maintained by Contractor in accordance with this Article, on the basis of its not complying with the Contract Documents, Owner will notify Contractor in writing thereof within ten (10) days of the date of delivery of such certificates to Owner in accordance with Section 2.7. Contractor shall provide to Owner such additional information in respect to insurance provided by Contractor as Owner may reasonably request.  Failure by Owner to give any such notice of objection within the time provided shall constitute acceptance of such insurance purchased by Contractor as complying with the Contract Documents.  With the prior approval of Owner, Contractor may substitute different types or amounts of coverage for those specified as long as the total amount of required protection is not reduced.

5.9	Partial Utilization Property Insurance.  If Owner finds it necessary to occupy or use a portion or portions of the Work prior to Substantial Completion of all the Work, such use or occupancy may be accomplished in accordance with Section 13.12; provided that no such use or occupancy shall commence before the insurers providing the property insurance have acknowledged notice thereof and in writing effected the changes in coverage necessitated thereby.  The insurers providing the property insurance shall consent by endorsement on the policy or policies, but the property insurance shall not be canceled or lapse on account of any such partial use or occupancy.

5.10	No Limit To Liability.  Nothing in this Article shall operate or be construed as limiting the amount of liability of Contractor to the above enumerated amounts.

## 5.11	Indemnification.

5.11.1 To the fullest extent permitted by Laws and Regulations, Contractor shall indemnify and hold harmless Owner and Engineer and the officers, directors, employees, agents and other consultants of each and any of them from and against all claims, costs, losses and damages (including but not limited to all fees and charges of engineers, architects, attorneys and other professionals and all court or arbitration or other dispute resolution costs) arising out of or resulting from the performance of the Work, provided that any such claim, cost, loss or damage: (i) is attributable to bodily injury, sickness, disease or death, or to injury to or destruction of tangible property (other than the Work itself), including the loss of use resulting therefrom, and (ii) is caused in whole or in part by any negligent act or omission of Contractor, any Subcontractor; any Supplier, any person or organization directly or indirectly employed by any of them to perform or furnish any of the Work or anyone for whose acts any of them may be liable, regardless of whether or not caused in part by any negligence or omission of a person or entity indemnified hereunder or whether liability is imposed upon such indemnified party by Laws and Regulations regardless of the negligence of any such person or entity.

5.11.2 In any and all claims against Owner or Engineer or any of their respective consultants, agents, officers, directors or employees by any employee (or the survivor or personal representative of such employee) of Contractor, any Subcontractor, any Supplier, any person or organization directly or indirectly employed by any of them to perform or furnish any of the Work, or anyone for whose acts any of them may be liable, the indemnification obligation under paragraph 5.11 shall not be limited in any way by any limitation on the amount or type of damages, compensation or benefits payable by or for Contractor or any such Subcontractor, Supplier or other person or organization under workers' compensation acts, disability benefit acts or other employee benefit acts.

5.11.3 The indemnification obligations of Contractor under paragraph 5.11 shall not extend to the liability of Engineer and Engineer's Consultants, officers, directors, employees or agents caused by the professional negligence, errors or omissions of any of them.

5.11.4 All representations, indemnifications, warranties and guarantees made in, required by or given in accordance with the Contract Documents, as well as all continuing obligations indicated in the Contract Documents, will survive final payment, completion and acceptance of the Work and termination or completion of the Agreement.

ARTICLE 6 - ContractorS RESPONSIBILITIES

6.1	Supervision.  Contractor shall supervise, inspect and direct the Work competently and efficiently, devoting such attention thereto and applying such skills and expertise as may be necessary to perform the Work in accordance with the Contract Documents.  Contractor shall be solely responsible for the means, methods, techniques, sequences and procedures of construction, but Contractor shall not be responsible for the negligence of others in the design or specification of a specific means, method, technique, sequence or procedure of construction which is shown or indicated in and expressly required by the Contract Documents.  Contractor shall be responsible to see that the completed Work complies strictly with the Contract Documents.

6.2	Resident Superintendent.  Contractor shall keep on the work site at all times during its progress a competent resident superintendent, who shall not be replaced without written notice to Owner and Engineer except under extraordinary circumstances.  The superintendent will be Contractor’s representative at the site and shall have authority to act on behalf of Contractor.  All communications given to or issued by the superintendent shall be as binding as if given to or issued by Contractor.

6.3	Personnel and Work Hours.  Contractor shall provide competent, suitably qualified personnel to survey, lay out and construct the Work as required by the Contract Documents.  Contractor shall at all times maintain good discipline and order at the site.  Except in connection with the safety or protection of persons or the Work or property at the site or adjacent thereto, and except as otherwise indicated in the Contract Documents, all Work at the site shall be performed during regular working hours, and Contractor will not permit overtime work or the performance of Work on Saturday, Sunday or any legal holiday without Owner's written consent given after prior written notice to Engineer.

6.4	Full Responsibility.  Unless otherwise specified in the Contract Documents, Contractor shall furnish and assume full responsibility for all materials, equipment, labor, transportation, construction equipment and machinery, tools, appliances, fuel, power, light, heat, telephone, water and sanitary facilities and all other temporary facilities and incidentals necessary for the furnishing, performance, testing, start-up and completion of the Work.

6.5	General Standards of Quality.  All materials and equipment shall be of good quality and new, except as otherwise provided in the Contract Documents.  All warranties and guarantees specifically called for by the Contract Documents shall expressly run to the benefit of Owner.  If required by Engineer or Owner, Contractor shall furnish satisfactory evidence (including reports of required tests) as to the kind and quality of materials and equipment.  All materials and equipment shall be applied, installed, connected, erected, used, cleaned and conditioned in accordance with the instructions of the applicable supplier, except as otherwise provided in the Contract Documents; but no provisions of any such instructions will be effective to assign to Owner, Engineer, or any of Engineer’s consultants, agents or employees, any duty or authority to supervise or direct the furnishing or performance of the Work or any duty or authority to undertake responsibility contrary to the provisions of Sections 8.10 or 8.11.

6.6	Progress Schedule.  Contractor shall adhere to the progress schedule established in accordance with paragraph 2.9 as it may be adjusted from time to time.  Contractor shall submit to Engineer for acceptance (to the extent indicated in Section 2.7) proposed adjustments in the progress schedule that will not change the Contract Times (or Milestones).  Such adjustments will conform generally to the progress schedule then in effect and additionally will comply with any provisions of the General Conditions applicable thereto.

6.7	Substitute or “Or Equal” Items.  Whenever, in the Contract Documents, an article, material, apparatus, equipment, or process is called for by trade name or by the name of a patentee, manufacturer, or dealer or by reference to catalogs of a manufacturer or dealer, It shall be understood as intending to mean and specify the article, material, apparatus, equipment, or process designated, or any approved equal thereto in quality, finish, design, efficiency and durability and equally serviceable for the purposes for which it is intended.  Whenever material or equipment is submitted by Contractor for approval as being equal to that specified, the submittal shall include sufficient information and data to demonstrate that the material or equipment conforms to all Contract requirements.  The decision as to whether or not such material or equipment is equal to that specified shall be made by the Owner in consultation with Engineer.  Neither the approval of alternate material or equipment as being equivalent to that specified nor the furnishing of the material or equipment specified, shall in any way relieve Contractor of responsibility for failure of the material or equipment, due to faulty design, material, or workmanship, to perform the functions required by the Contract Documents.

6.8	Engagement of Subcontractors, Suppliers and Others. General Contractor must contribute at least 15% of the contract price in work, materials services or any combination thereof.  Contractor shall not employ any Subcontractor, Supplier or other person or organization, whether initially or as a substitute, against whom Owner or Engineer may have reasonable objection.  Contractor shall not be required to employ any Subcontractor, Supplier or other person or organization to furnish or perform any of the Work against whom Contractor has reasonable objection.  If the Contract Documents require the identity of certain Subcontractors, Suppliers or other persons or organizations (including those who are to furnish the principal items of materials and equipment) to be submitted to Owner prior to the Effective Date of the Agreement, for acceptance by Owner and Engineer, and if Contractor has submitted a list thereof in accordance with the Contract Documents, Owner's or Engineer's acceptance or acquiescence as to any such Subcontractor, Supplier or other person or organization so identified may be revoked on the basis of reasonable objection after due investigation, in which case Contractor shall submit an acceptable substitute, in which case the Contract Price will be adjusted by the difference in the cost occasioned by such substitution and an appropriate Change Order will be issued or Written Amendment signed.  No acceptance by Owner or Engineer of any such Subcontractor, Supplier or other person or organization shall constitute a waiver of any right of Owner or Engineer to reject Defective Work.

6.9	Responsibility For Others.  Contractor shall be fully responsible to Owner and Engineer for all acts and omissions of his Subcontractors, Suppliers and other persons and organizations performing or furnishing any of the Work under a direct or indirect contract with Contractor just as Contractor is responsible for Contractor’s own acts and omissions.  Nothing in the Contract Documents shall create for the benefit of any such Subcontractor, Supplier or other person or organization any contractual relationship between Owner or Engineer and any Subcontractor, Supplier or other person or organization, except as to warranties enforceable by Owner as against such parties, nor shall it create any obligation on the part of Owner or Engineer to pay or to see to the payment of any moneys due any such Subcontractor, Supplier or other person or organization, except as may otherwise be required by Laws and Regulations.

6.9.1	Contractor shall be solely responsible for scheduling and coordinating the Work of Subcontractors, Suppliers and other persons and organizations performing or furnishing any of the Work under a direct or indirect contract with Contractor.

6.9.2	Contractor shall require all Subcontractors, Suppliers and such other persons and organizations performing or furnishing any of the Work to communicate with the Engineer through Contractor.

6.9.3	Owner or Engineer may furnish to any such Subcontractor, Supplier, or other person or organization, to the extent practicable, information about amounts paid to Contractor in accordance with Contractor's Applications for Payment on account of the particular Sub-contractor's, Supplier's, other person's, or other organization's work.

6.10	Allocation of Work.  The sections of the Specifications and the identifications of any Drawings shall not control Contractor in dividing the Work among Subcontractors or Suppliers or delineating the Work to be performed by any specific trade.

6.11	Subcontract Provisions.  All Work performed by Subcontractors will be pursuant to an appropriate agreement between Contractor and the Subcontractor which specifically binds the Subcontractor to these General Conditions and the applicable terms and conditions of all other Contract Documents for the benefit of the Owner and Engineer. Whenever any such agreement is with a Subcontractor or Supplier who is listed as an additional insured on the property insurance provided in paragraph 5.5 or 5.6, the agreement between the Contractor and the Subcontractor or/Supplier will contain provisions whereby the Subcontractor or Supplier waives all rights against Owner, Contractor and Engineer and all other additional insureds for all losses and damages caused by, arising out of or resulting from any of the perils covered by such policies and any other property insurance applicable to the Work. If the insurers on any such policies require separate waiver forms to be signed by any Subcontractor or Supplier, Contractor will obtain the same.

6.12	Patent Fees and Royalties. Contractor shall pay all license fees and royalties and assume all costs incident to the use in the performance of the Work or the incorporation in the Work of any invention, design, process, product or device which is the subject of patent rights or copyrights held by others.  If a particular invention, design, process, product or device is specified in the Contract Documents for use in the performance of the Work and if to the actual knowledge of Owner or Engineer its use is subject to patent rights or copyrights calling for the payment of any license fee or royalty to others, the existence of such rights shall be disclosed by Owner in the Contract Documents.  To the fullest extent permitted by Law, Contractor shall indemnify and hold harmless Owner and Engineer and anyone directly or indirectly employed by either of them from and against all claims, costs, attorneys’ fees, damages, losses and expenses (including attorney fees and court and arbitration costs) arising out of or resulting from any infringement of patent rights or copyrights incident to the use in the performance of the Work or resulting from the incorporation in the Work of any invention, design, process, product or device not specified in the Contract Documents, and shall defend at it sole cost, if requested by Owner or Engineer, all such claims in connection with any alleged infringement of such rights.

6.13	Permits.  Unless otherwise provided in the Contract Documents, Contractor shall obtain and pay for all construction permits and licenses.  Owner shall assist Contractor, when necessary, in obtaining such permits and licenses.  Contractor shall pay all governmental charges and inspection fees necessary for the prosecution of the Work, which are applicable at the time of opening of Bids.  Contractor shall pay all charges of utility owners for connections to the Work, and Owner shall pay all charges of such utility owners for capital costs related thereto such as plant investment fees.

6.14	Laws and Regulations.  Contractor shall give all notices and comply with all Laws and Regulations in effect during the furnishing and performance of the Work.  Except where otherwise expressly required by applicable Laws and Regulations, neither Owner nor Engineer shall be responsible for monitoring Contractor’s compliance with Laws or Regulations.  If Contractor performs any Work knowing or having reason to know that it is contrary to Laws or Regulations, Contractor bear all claims, costs, losses and damages caused by, arising out of or resulting therefrom; however, it shall not be Contractor’s primary responsibility to make certain that the Specifications and Drawings are in accordance with Laws and Regulations, however, this shall not relieve Contractor of Contractor’s obligations under this paragraph or under Section 2.6 or Section 3.3. If Contractor performs any Work knowing or having reason to know that it is contrary to such Laws and Regulations, and without such notice to Engineer and Owner, Contractor shall bear the risk of all claims, costs, losses and damages caused by, arising out of or resulting therefrom.

6.15	Taxes.  Contractor shall pay all sales, consumer, use and other similar taxes required to be paid by Contractor in accordance with the Laws and Regulations applicable to the place where the Project is located.  Owner is required by statute to withhold certain taxes, including Indiana State Gross Income tax, from all payments made to non-resident contractors who are corporations and to remit such tax quarterly to the Indiana Department of Revenue.  A foreign corporation, which is registered with the Indiana Secretary of State to do business in Indiana, shall be exempt from this withholding requirement.  Exemption certificates for the Indiana Gross Retail tax (sales tax) for property that becomes property of Owner and all Federal Excise tax can be furnished by Owner and therefore such taxes shall not be included in the Contract Price.  Contractor may request exemption certificate forms directly from Owner.

6.16	Use of Premises. Contractor shall confine construction equipment, the storage of materials and equipment and the operations of workers to the Project site and land and areas identified in and permitted by the Contract Documents, and other land and areas permitted by Laws and Regulations, rights-of-way, permits and easements, and shall not unreasonably encumber the premises with construction equipment or other materials or equipment.  Contractor shall assume full responsibility for any damage to any such land or area, or to the owner or occupant thereof or of any adjacent land or areas contiguous thereto, resulting from the performance of the Work.  Should any claim be made by any such owner or occupant because of the performance of the Work, Contractor shall promptly settle with such other party by negotiation or otherwise resolve the claim by arbitration, other dispute resolution proceeding or at law.  Contractor shall, to the fullest extent permitted by Laws and Regulations, indemnify and hold Owner and Engineer harmless from and against all claims, damages, losses and expenses (including, but not limited to, fees of engineers, architects, attorneys and other professionals and court and arbitration costs) arising directly, indirectly or consequentially out of any action, legal or equitable, brought by any such other party against Owner or Engineer to the extent based on a claim arising out of Contractor's performance of the Work

6.17	Control of Waste. During the progress of the Work, Contractor shall keep the premises free from accumulations of waste materials, rubbish and other debris resulting from the Work.  At the completion of the Work Contractor shall remove all waste materials, rubbish and debris from and about the premises as well as all tools, appliances, construction equipment, machinery and surplus materials, and shall leave the site clean and ready for occupancy by Owner.  Contractor shall restore to original condition all property not designated for alteration by the Contract Documents.

6.18	Loads on Structures. Contractor shall not load nor permit any part of any structure to be loaded in any manner that will endanger the structure, nor shall Contractor subject any part of the Work or adjacent property to stresses or pressures that will endanger it.

6.19	Record Documents. Contractor shall maintain in a safe place at the site one record copy of all Specifications, Drawings, Addenda, Written Amendments, Change Orders, Work Change Directives, Field Orders and written interpretations and clarifications (issued pursuant to Section 8.4) in good order and annotated to show all changes made during construction.  These record documents together with all approved samples and a counterpart of all approved Shop Drawings will be available to Engineer for reference.  Upon completion of the Work, these record documents, samples and Shop Drawings shall be delivered to Engineer for Owner as a condition to Contractor’s right to receive final payment.

6.20 	Safety and Protection.

6.20.1	Contractor shall be solely responsible for initiating, maintaining and supervising all safety precautions and programs in connection with the Work and shall take all necessary precautions for the safety of, and provide the necessary protection to prevent damage, injury or loss to (i) all employees on the Work and other persons and organizations who may be affected thereby, (ii) all the Work and all materials or equipment to be incorporated therein, whether in storage on or off the site, and (iii) other property at the site or adjacent thereto, including trees, shrubs, lawns, walks, pavements, roadways, structures, utilities and Underground Facilities not designated for removal, relocation or replacement in the course of construction.

6.20.2	Contractor shall comply with all applicable Laws and Regulations of any public body having jurisdiction for the safety of persons or property or to protect them from damage, injury or loss; and shall erect and maintain all necessary safeguards for such safety and protection.  Contractor shall notify owners of adjacent property, owners of Underground Facilities and utility owners when prosecution of the Work may affect them, and shall cooperate with them in the protection, removal, relocation and replacement of their property.  All damage, injury or loss to any property referred to in Section 6.20.1 caused, directly or indirectly, in whole or in part, by Contractor, any Subcontractor or Supplier, or any other person or organization directly or indirectly employed by any of them to perform or furnish any of the Work or anyone for whose acts any of them may be liable, shall be remedied by Contractor (except damage or loss attributable to the fault of Drawings or Specifications or to the acts or omissions of Owner or Engineer or anyone employed by either of them or anyone for whose acts either of them may be liable, and not attributable, directly or indirectly, in whole or in part, to the fault or negligence of Contractor).   Contractor’s duties and responsibilities for the safety and protection of the Work shall continue until such time as all the Work is completed and Engineer has issued a notice to Owner and Contractor in accordance with Section 13.11 that the Work is acceptable (except as otherwise expressly provided in connection with Substantial Completion).

6.20.3	Pursuant to I.C. 36-1-12-20, all Work which requires the creation of a trench or hole of at least five (5) feet in depth, shall be provided with a trench safety system.  Trench safety systems shall meet all of the requirements of IOSHA Regulations 29 C.F.R. 1926, Subpart P or other applicable safety standards and regulations.  The cost or compliance with any and all such regulations shall be borne by the Contractor without any increase in the Contract Price.  Owner shall pay for the trench safety system as a separate pay item if one is provided on unit cost work; or, if a separate pay item is not provided, Owner shall pay for the safety system as part of the pay item or schedule of values item for the principal Work with which the safety system is associated, as determined by Engineer.

6.20.4	Contractor shall designate a responsible representative at the site whose duty shall be the prevention of accidents.  This person shall be Contractor’s superintendent unless otherwise designated in writing by Contractor to Owner.

6.20.5	Contractor shall be responsible for coordinating any exchange of material safety data sheets or other hazard communication information required to be made available to or exchanged between or among employers at the site in accordance with Laws or Regulations.

6.21	Emergencies.  In emergencies affecting the safety or protection of persons or the Work or property at the site or adjacent thereto, Contractor, without special instruction or authorization from Engineer or Owner, is obligated to act to prevent threatened damage, injury or loss.  Contractor shall give Engineer and Owner immediate written notice if Contractor believes that any significant changes in the Work or variations from the Contract Documents are caused thereby.  If Owner determines that a change in the Contract Documents is required because of the action taken in response to an emergency, a Work Change Directive or Change Order will be issued to document the consequences of the changes or variations.

6.22	Shop Drawings and Working Drawings.

6.22.1	Contractor shall promptly prepare and submit layout, detail and shop drawings to insure proper construction, assembly, and installation of the Work using those materials and equipment specified in the Technical Specifications.  Such drawings will be known as “Working Drawings”.  A schedule of Working Drawings submissions shall be submitted for Engineer’s approval on a form acceptable to Engineer within ten (10) days of the effective date after the signing of the Agreement by Owner

6.22.2	Working Drawings shall be numbered consecutively and shall accurately and distinctly present (i) all working and erection dimensions, (ii) arrangements and sectional views, (iii) necessary details, including complete information for making connections between Work under this Contract and work under other contracts, (iv) electrical wiring connections between all equipment furnished under the Contract, including all internal wiring between internal components of equipment, (v) kinds of materials and finishes, and (vi) parts lists and description thereof.

6.22.3	Drawings for mechanical and electrical equipment shall present, where applicable, such data as dimensions, weight and performance characteristics.  This data shall show conformance with the performance characteristics and other criteria incorporated in the Contract Documents.  Each drawing or page shall include (i) submittal date and revision dates, (ii)	project name, division number and descriptions, (iii) Detailed Specifications section number and page number, (iv) identification of equipment, product or material, (v) name of Contractor and Subcontractor, (vi) name of Supplier and Manufacturer, (vii) relation to adjacent structure or material, (viii) field dimensions, clearly identified, (ix) ASTM, Federal and other Specification references, (x) space for Engineer's stamps (xi) identification of deviations from the Contract Documents, (xii) Contractor’s stamp, initialed or signed, dated and certifying to review of submittal, certification of field measurements and compliance with Contract, and (xiii) location at which the equipment or materials are to be installed (both physical location and location relative to other connected or attached material).  Engineer will return, unchecked, any submittal which does not contain complete data on the Work and full information on related matters.  Stock or standard drawings will not be accepted for review unless full identification and supplementary information is shown thereon in ink or typewritten form.

6.22.4	Contractor shall check and approve all Working Drawings before transmitting them to Engineer to determine that they comply with requirements of the Contract Documents.  Drawings which are incomplete or are not in compliance with the Contract Documents shall not be submitted for processing by Engineer.  Contractor shall place his signature or initials on his stamp of approval on all Working Drawings submitted to Engineer to indicate compliance with this requirement.  Contractor's approval shall constitute a representation that all quantities, dimensions, field construction criteria, materials, catalog numbers, performance criteria and similar data have been verified and that, in his opinion, the submittal fully meets the requirements of the Contract Documents.  Contractor shall schedule, prepare and submit all working drawings in accordance with a time-table that will allow his Suppliers and Manufacturers sufficient time to fabricate, manufacture, inspect, test and deliver their respective products to the project site in a timely manner so as to not delay the complete performance of the Work.  The time-table so developed shall be in conformance with the completion dates specified in the Agreement.

6.22.5	If the Working Drawings show departures from the Contract requirements, Contractor shall make specific mention thereof in his letter of transmittal, otherwise approval of such submittals by Engineer shall not constitute approval of the departure.  Approval of the drawings shall constitute approval of the subject matter thereof only and not of any structure, material, equipment or apparatus shown or indicated.

6.22.6	The approval of Working Drawings will be general and shall not relieve Contractor of responsibility for the accuracy of such drawings, nor for the proper fitting and construction of the Work, nor for the furnishing of materials or work required by the Contract and not indicated on the drawings.  No Work called for by Working Drawings shall be done until such drawings have been approved by Engineer.

6.22.7	The procedure in seeking approval of the Working Drawings shall be as follows:

.1	Contractor shall submit six (6) complete sets of drawings and other descriptive data together with six (6) copies of a letter of transmittal to Engineer for approval.  The letter of transmittal shall contain the name of the Project, Workmanship and Materials section number, the name of Contractor, the list of drawings submitted including numbers and titles, requests for any approval of departures from the contract requirements and any other pertinent information.

.2	Drawings or descriptive data will be stamped "Approved”, “Approved as Noted”, or “Not Approved” by the Engineer, and one (1) copy with a letter of transmittal will be returned to Contractor.

.3	If a drawing or other data is stamped "Approved”, Contractor shall insert the date of approval on six (6) additional copies of the document and transmit the six (6) copies to Engineer together with one copy of a letter of transmittal containing substantially the same information required in Sub-Section .1.

.4	If a drawing or other data is stamped “Approved as Noted', Contractor shall make the corrections indicated and proceed as in Sub-Section .3.

.5	If a drawing or data is stamped “Not Approved”, Contractor shall make the necessary corrections and resubmit the documents as required in Sub-Section .1. The letter transmitting corrected documents shall indicate that the documents comprise a resubmittal.

.6	If any corrections, other than those noted by Engineer, are made on a Working Drawing prior to resubmittal, such changes must be pointed out by Contractor upon resubmittal.

.7	Contractor shall revise and resubmit the Working Drawings as required until approval thereof is obtained.  Costs associated with the Engineer’s review of any third and subsequent submittals shall be borne by Contractor.  Contractor shall be billed for these costs by Owner or the Owner may deduct such costs from subsequent payment.

6.23	Continuing the Work. Contractor shall carry on the Work and adhere to the progress schedule during all disputes or disagreements with Owner.  No Work shall be delayed or postponed pending resolution of any disputes or disagreements, except as permitted by Section 14.5 or as Contractor and Owner may otherwise specifically agree in writing.  Any work stoppage, delay, suspension or significant reduction in manpower, or removal of equipment from the site, determined by the Engineer or Owner to have occurred by reason of any such unresolved dispute or disagreement shall constitute an event of default thereby subjecting Contractor to termination of the Contract.

6.24	Subcontractor and other Liens.  Contractor agrees and warrants to the Owner that no claim or lien shall attach to or be filed on the Project by virtue of Contractor’s default in paying any employee, subcontractor or supplier.  Should such claim or lien be filed, payment otherwise due the Contractor will not be due until Contractor delivers to Owner a complete release of such claim or lien, or, at Owner’s option, a bond satisfactory to Owner indemnifying Owner against such claim or lien.

6.25	Installation of Utility Service.  Contractor shall assume all responsibility for proper installation of utility services to meet all rules and regulations of all utility companies or government agencies involved.  It is the responsibility of Contractor to provide a complete service and provide all work necessary to coordinate the Work with the work of the utility companies.

6.26	Damage, Survey and Correction.  Contractor, accompanied by a representative of Owner and/or Engineer, shall make a damage survey of the work site and adjacent properties prior to commencing the Work and before making application for final payment for the Work.  Contractor shall provide Owner a written inventory of damage observed during each survey.  Contractor shall replace or repair all existing construction and facilities (both surface and subsurface) including, but not limited to, sidewalks, fences, yards, plantings, mechanical services and electrical services which may be damaged in the performance of the Work.  All damage shall be corrected and such facilities shall be restored to their original condition.  Materials and construction shall be new and equal in quality, design, workmanship and installation to the existing material and construction.

6.27	Damage Notification. Contractor shall notify Engineer immediately upon observing damage to the site regardless of whether or not the damage is the result of Contractor's operations.

6.28	Employee Compensation.    Contractor may not pay employees in cash.  Contractors must certify that they are in compliance with the federal Fair Labor Standards Act (FLSA) and the Indiana Minimum Wage Law.

6.29	Contractor Employee Drug Testing Program.	When the estimated cost of the project exceeds $150,000, the Contractor must submit in the bid paperwork a written plan for a program to test the Contractor’s employees for drugs that is consistent with IC 4-13-18-5.  The requirement for a drug testing program applies to all Subcontractors.  Failure to comply with the drug testing program will result in cancellation of the contract.

.

ARTICLE 7 - WORK BY THIRD PARTIES

- Separate Work By Others.  Owner may perform other work related to the Project at the site by Owner’s own forces, have other work performed by utility owners or their contractors or let other direct contracts which shall contain General Conditions similar to these.  If the performance of such work is not reasonably indicated by the Contract Documents or is not reasonably inferable therefrom or otherwise inherent in connection with the Work as described by the Contract Documents as such work relates to the overall Project, written notice thereof will be given to Contractor prior to starting any such other work; and, if Contractor believes that such performance requires additional time, and the parties are unable to agree as to the extent thereof, Contractor may make a claim therefore as provided in Article 11.  Contractor shall afford each utility owner or its contractors and any other contractor who is a party to such a direct contract, or Owner's employees if Owner is performing work with its own forces, proper and safe access to the site and reasonable opportunity for the proper, efficient and timely performance of such work and for introduction and storage of materials and equipment, and shall properly connect and coordinate the Work with the work and activities of such other parties.  Contractor shall do all cutting, fitting and patching of the Work that may be required to make its several parts come together properly and integrate with such other work.  Contractor shall not endanger any work of others by cutting, excavating or otherwise altering their work and will only cut or alter their work with the written consent of Engineer and the others whose work will be affected.  The duties and responsibilities of Contractor under this Section are for the benefit of and may be directly enforced by such utility owners and other separate contractors to the extent that there are comparable provisions for the benefit of the Contractor in said direct contracts between Owner and such utility owners and other contractors.

- Inspecting Other Work.  If the proper execution or results of any part of Contractor’s Work depends upon the work of any such other contractor or utility owner or Owner’s forces, Contractor shall inspect and promptly report to Engineer in writing any delays, defects or deficiencies in such work that render it unavailable or unsuitable for such proper execution and results or that hinder or otherwise impact the Work to be performed by Contractor.  Contractor’s failure to report will constitute an acceptance of the other work as fit and proper for integration with Contractor’s Work except for latent or non-apparent defects and deficiencies in the other work.

- Coordination.  Contractor shall schedule the Work such that it shall cause no delay in the work of the other contractors.  Engineer will monitor the Contractor’s coordination of its Work with the work of other contractors.  Where coordination and scheduling conflicts arise between the Work and the work of other contractors on the site, Engineer will provide input to resolve the conflict, but such input or monitoring by the Engineer shall not relieve the Contractor of its obligations in respect of coordination with other contractors.  Except as provided in Section 11.4, Contractor shall have no claim against Owner for delays, disruptions or hindrances caused by other contractors who may be operating at the site, including, without limitation, delays resulting from lack of coordination.  Should Contractor cause damage to another contractor or subcontractor employed on the Project, Contractor agrees to settle with such other contractor or subcontractor by agreement, if the other party will so settle.  If such other contractor or subcontractor sues Owner or Engineer on account of damage alleged to have been sustained, Owner or Engineer as applicable, shall notify Contractor and Contractor shall bear the cost of defending such proceedings, and if a judgment or award in arbitration against Owner or Engineer arises therefrom, Contractor shall pay or satisfy said judgment, and pay all cost incurred by Owner or Engineer, including attorney fees.

ARTICLE 8 - Owner’S AND Engineer'S STATUS DURING CONSTRUCTION

8.1	Owner’s Representative. Engineer will be Owner’s representative during the construction period.  The duties and responsibilities and the limitations of authority of Engineer as Owner’s representative during construction are set forth in the Contract Documents and shall not be extended without written consent of Owner and Engineer.

8.2	Visits to Site.  Engineer will make visits to the site at intervals appropriate to various stages of construction to observe and become cognizant with the progress, quality and quantity of the executed Work and to determine, in general, if the Work is proceeding in accordance with the Contract Documents.  Engineer will also, as he deems necessary, make on-site inspections to check the quality or quantity of the Work.  Engineer's efforts will be undertaken solely for the purpose of providing Owner a greater degree of confidence that all Work will conform to the Contract Documents.  On the basis of such visits and on-site observations as an experienced and qualified design professional, Engineer will keep Owner informed of the progress of the Work and will endeavor to guard Owner against defects and deficiencies in the Work.

8.3	Project Representation.  Owner may, at its sole option, assign one or more full or part time engineers, inspectors or other representatives to observe the performance of the Work.  The duties, responsibilities and limitations of authority of any such representatives will be as provided in the General Conditions or as otherwise stated to Contractor in writing by the Director or other duly appointed official of the department or agency of the Owner for whose use and/or benefit the Project is to be constructed.

8.4	Clarifications and Interpretations.  Engineer will issue with reasonable promptness written clarifications or interpretations of the requirements of Contract Documents (in the form of Drawings or otherwise) as Engineer may determine necessary, which shall be consistent with the intent of and reasonably inferable from the Contract Documents.  Such clarifications and interpretations shall become binding upon the Contractor upon ratification thereof by the Owner.  If Contractor believes that a written clarification or interpretation justifies an increase in the Contract Price or an extension of the Contract Time and the parties are unable to agree to the amount or extent thereof, Contractor may make a claim therefore as provided in Article 10 or Article 11.

8.5	Authorized Variations in Work. Owner, or Engineer following consultation with and approval by the Owner, may authorize minor variations in the Work requirements of the Contract Documents which do not involve an adjustment in the Contract Price or the Contract Time and are consistent with the overall intent of the Contract Documents.  These may be accomplished by a Field Order or other form of written directive and will be binding on Owner, and also on Contractor who shall perform the Work involved promptly.  If Owner or Contractor believes that a Field Order or other written directive issued pursuant to this Section justifies an adjustment in the Contract Price or an extension of the Contract Time, Contractor shall make a claim therefore as provided in Article 10 or 11.

8.6	Rejecting Defective Work. Owner or Engineer will have authority to disapprove or reject Work which is believed or determined to be defective, and will also have authority to require special inspection or testing of the Work as provided in Section 12.4, whether or not the Work is fabricated, installed or completed.

8.7	Engineer’s Interpretations and Decisions.

8.7.1 	Engineer will determine the actual quantities and classifications of Unit Price Work performed by Contractor. Engineer will review with Contractor the Engineer's preliminary determinations on such matters before rendering a written decision thereon (by recommendation of an Application for Payment or otherwise). Engineer's written decision thereon will be final and binding upon Owner and Contractor, unless, within ten (10) days after the date of any such decision, either Owner or Contractor delivers to the other and to Engineer written notice of intention to appeal from Engineer's decision and formal proceeding is instituted by the appealing party in a forum of competent jurisdiction to exercise such rights or remedies as the appealing party may have with respect to Engineer's decision, unless otherwise agreed in writing by Owner and Contractor.

8.7.2	Engineer will be the initial interpreter of the requirements of the Contract Documents and judge of the acceptability of the Work thereunder to the extent that such requirements and issues respecting acceptability of the Work involve decisions or interpretations dealing with technical, engineering, design or other subject matters, arising out of the Technical Specifications and within the expertise of the Engineer.  Written notice of each such claim, dispute and other matter will be delivered by the claimant to Engineer and the other party to the Agreement promptly (but in no event later than twenty (20) days) after the start of the notice of the event giving rise thereto, and written supporting data will be submitted to Engineer and the other party within thirty (30) days of such occurrence unless Engineer allows an additional period of time for the submission of additional or more accurate data in support of the claim, dispute or other matter.  The opposing party shall submit any response to the Engineer and the claimant within thirty (30) days after receipt of the claimant’s last submittal (unless the Engineer allows additional time).  The Engineer will render a formal decision in writing within thirty (30) days after receipt of the opposing party’s submittal, if any, in accordance with this section.  Engineer's written decision on such claim, dispute or other matter will be final and binding upon Owner and Contractor unless a written notice of intention to appeal from Engineer's written decision is delivered by Owner or Contractor to the other and to Engineer within thirty (30) days after the date of such decision and a formal proceeding is instituted by the appealing party in a forum of competent jurisdiction to exercise such rights or remedies as the appealing party may have with respect to such claim, dispute or other matter in accordance with applicable Laws and Regulations within thirty (30) days of the date of such decision, unless otherwise agreed in writing by Owner and Contractor.

8.8	Non-liability of Engineer. Neither Engineer’s authority to act under this Article or elsewhere in the Contract Documents nor any decision made by Engineer in good faith, either to exercise or not to exercise such authority, shall give rise to any duty or responsibility of Engineer to Contractor, any Subcontractor, any Supplier, or any other person or organization performing any of the Work, or to any surety for any of them.

- Purposes of Engineer’s Activities.  Whenever in the Contract Documents the terms “as ordered”,  "as directed”, “as required”, “as allowed”, “as approved” or terms of like effect or import are used, or the adjectives “reasonable”, “suitable”, "acceptable”, “proper” or “satisfactory” or adjectives of like effect or import are used to describe requirement, direction, review or judgment of Engineer as to the Work, it is intended that such requirement, direction, review or judgment will be solely to evaluate the Work for compliance with the Contract Documents (unless there is a specific statement indicating otherwise).  The use of any such term or adjective shall not be effective to assign to Engineer any duty or authority to supervise or direct the furnishing or performance of the Work or any duty or authority to undertake responsibility contrary to the provisions of this Article.

8.10	Construction Methods.  Owner and Engineer shall have no responsibility for Contractor's selection or implementation of means, methods, techniques, sequences or procedures of construction, or the safety precautions and programs incident thereto, and Owner and Engineer will not be responsible for Contractor's failure to perform or furnish the Work or to fulfill other duties in accordance with the Contract Documents.

8.11	Acts or Omissions By Others. Owner and Engineer will not be responsible for the acts or omissions of Contractor or of any Subcontractors, any Supplier, or of any separate contractor or other person or organization furnishing any work, labor, materials or services for or in furtherance of the Project.

8.12	Communications. Owner may issue all communication to Contractor through Engineer or at its option may communicate with the Contractor directly, with a copy to the Engineer.

8.13	Replacement for Engineer. In case of termination of the employment of Engineer, Owner shall appoint an engineer whose status under the Contract Documents shall be that of the former Engineer; provided, that Owner may, at its sole option and with notice to Contractor, elect to exercise all or part of the function and authority of the Engineer following such termination, either permanently or on an interim basis.

ARTICLE 9 - CHANGES IN THE WORK

9.1	Owner’s Right To Initiate Changes.  Without invalidating the Agreement and without notice to any surety, Owner may at any time order additions, deletions or revisions in the Work.  Such changes will be authorized by a Written Amendment, a Change Order or a Work Change Directive.  Upon receipt of any such document, Contractor shall promptly proceed with the Work involved, which will be performed under the applicable provisions of the Contract Documents except as otherwise specifically provided.

9.2	Inability To Agree on Price or Time Adjustments.  If Owner and Contractor are unable to agree as to the extent, if any, of an increase or decrease in the Contract Price or an extension or shortening of the Contract Time that should be allowed as a result of an Owner-initiated change, a claim may be made therefore as provided in Article 10 or Article 11.

9.3	Non-Required Work. Contractor shall not be entitled to an increase in the Contract Price or an extension of the Contract Time with respect to any Work performed that is not required by the Contract Documents, as amended, modified and supplemented as provided in Sections 3.4 and 3.5, except in the case of an emergency as provided in Section 6.21 and except in the case of uncovering Work as provided in Section 12.4.

9.4	Change Orders and Amendments.  Owner and Contractor shall execute appropriate Change Orders or Written Amendments covering (i) changes to the Work which are ordered by Owner pursuant to Section 9.1, are required because of acceptance of Defective Work under Section 12.8 or correcting Defective Work under Section 12.9; (ii) changes in the Contract Price or Contract Time which are agreed to by the parties; and (iii) changes in the Contract Price or Contract Time which embody the substance of any written decision rendered by Engineer pursuant to Section 8.7, provided that, in lieu of executing any such Change Order, an appeal may be taken from any such decision in accordance with the provisions of the Contract Documents and applicable Laws and Regulations, but during any such appeal, Contractor shall carry on the Work and adhere to the progress schedule as provided in Section 6.23.

## 9.5	Notification to Surety.  If notice of any change affecting the general scope of the Work or the provisions of the Contract Documents (including, but not limited to, Contract Price or Contract Times) is required by the provisions of any Bond to be given to a surety, the giving of any such notice will be Contractor's responsibility, and the amount of each applicable Bond will be adjusted accordingly.

ARTICLE 10 - CHANGE OF CONTRACT PRICE

10.1	Items Included in Contract Price.  The Contract Price constitutes the total compensation (subject to authorized adjustments) payable to Contractor for performing the Work and assuming all obligations and risks as provided by the Contract Documents.  All duties, responsibilities and obligations assigned to or undertaken by Contractor shall be at his expense without change in the Contract Price.

10.2	Changes in Contract Price. The Contract Price may only be changed by a Change Order or by a Written Agreement.  Any claim for an increase or decrease in the Contract Price shall be based on written notice delivered by the party making the claim to the other party and Engineer promptly (but in no event later than twenty (20) days) after the start of the occurrence of the event or the commencement of a series of events giving rise to the claim.  Notice of the amount of the claim with supporting data shall be delivered to the other party and Engineer within thirty (30) days after the start of such occurrence or event after the required notice (unless Engineer allows an additional period of time for claimant to submit additional or more accurate date in support of the claim.  A written statement of the amount claimed by claimant shall be conclusively presumed to include all direct, indirect and consequential amounts claimed or to be claimed by claimant as a result of all facts, occurrences and events giving rise thereto.  Nothing provided in this Section shall be construed to afford the Contractor any rights or claims otherwise precluded by any other provisions of these General Conditions or other Contract Documents.  The burden of proof for such claim shall be on claimant.

10.3	Value of Affected Work. The value of any Work affected by a Change Order, or any Written Agreement, or of any increase or decrease in the Contract Price in respect of Owner-initiated changes or Contractor claims as provided by this Section shall be determined in one of the following ways:

10.3.1	For Work covered in whole or in part by unit prices contained in the Contract Documents, by application of such unit prices to the quantities of the contract items involved, unless otherwise provided in the Contract Documents;

10.3.2	For items or elements of Work not covered by unit prices, by mutual acceptance of a lump sum or unit price; or, if no such agreement is reached, on the basis of the Cost of the Work (determined as provided in Sections 10.4 and 10.5) plus a reasonable allowance for Contractor’s profit and overhead based on a percentage of the Cost of Work not to exceed ten percent (10%), or such different percentage as may be specified by other Contract Documents.

10.4	Cost of The Work. The term Cost of the Work means the sum of all costs necessarily incurred and paid by Contractor in the proper and efficient performance of the particular Work for which costs thereof are to be determined.  Except as otherwise may be agreed to in writing by Owner, such costs shall be in amounts no higher than those prevailing in the locality of the Project.  Such costs shall not include any of the costs itemized in Section 10.5 and may include only the following items:

10.4.1	Payroll costs for employees in the direct employ of Contractor in the performance of the affected Work under schedules of job classifications agreed upon by Owner and Contractor.  Such employees shall include without limitation superintendents, foremen and other personnel employed full time at the site.  Payroll costs for employees not employed full time on the Work shall be apportioned on the basis of their time spent on such Work. Payroll costs shall include, but not be limited to, salaries and wages plus the cost of fringe benefits which shall include social security contributions, unemployment, excise and payroll taxes, workers' or workmen's compensation, health and retirement benefits, bonuses, sick leave, vacation and holiday pay applicable thereto.  Such employees shall not include superintendents or other management and supervisory personnel whose costs are included in the Contract Price.  The expenses of performing Work after regular working hours, on Saturday, Sunday or legal holidays shall be included only if previously authorized by Owner in writing.

10.4.2	Cost of all materials and equipment properly furnished and incorporated in the Work, including costs of transportation and storage thereof, and field services by suppliers or manufacturers required in connection therewith.  All cash discounts shall accrue to Contractor unless Owner deposits funds with Contractor with which to make payments, in which case cash discounts shall accrue to Owner.  All trade discounts, rebates and refunds, and all returns from sale of surplus materials and equipment shall accrue to Owner and Contractor shall make provisions so that they may be obtained.

10.4.3	Payments made by Contractor to Subcontractors for affected Work performed or furnished by Subcontractors.  If required by Owner, Contractor shall obtain competitive bids from Subcontractors acceptable to Owner and Contractor and shall deliver such bids to Owner who will then determine, with the advice of Engineer, which bids will be accepted.  If a subcontract provides that the Subcontractor is to be paid on the basis of cost of the affected Work Plus a fee, Subcontractor’s cost of such Work shall be determined in the same manner as Contractor’s Cost of the Work.  All subcontracts shall be subject to the other provisions of the Contract Documents insofar as applicable.

10.4.4	Cost of special consultants (including, but not limited to, engineers, architects, testing laboratories, surveyors, attorneys and accountants) employed for services specifically related to the affected Work.

10.4.5	Supplemental costs including the following:

.1	The proportion of necessary transportation, travel and subsistence expenses of Contractor’s employees incurred in discharge of duties connected with the affected Work.

.2	Costs, including transportation and maintenance, of all materials, supplies, equipment, machinery, appliances, office and temporary facilities at the site and hand tools not owned by the workers, which are consumed in the performance of the affected Work, and cost less market value of such items used but not consumed which remain the property of Contractor.

.3	Rentals of all construction equipment and machinery and the parts thereof whether rented from Contractor or others in accordance with rental agreements approved by Owner with the advice of Engineer, and the costs of transportation, loading, unloading, installation, dismantling and removal thereof all in accordance with terms of said rental agreements.  The rental of any such equipment, machinery or parts shall cease when the use thereof is no longer necessary for the affected Work.  When construction equipment is owned by Contractor, the cost of such equipment shall be in accordance with U.S. Army Corps of Engineers publication titled “Construction Equipment Ownership and Operating Schedule” for Region II.

.4	Sales, consumer, sue or similar taxes related to the affected Work, and for which Contractor is liable, imposed by Laws or Regulations.

.5	Deposits lost for causes other than negligence of Contractor, any Subcontractor or anyone directly or indirectly employed by any of them or for whose acts any of them may be liable, and royalty payments and fees for permits and licenses.

.6	Losses, damages, and expenses caused by damage to the Work not compensated by insurance or otherwise, related to the Work or otherwise sustained by Contractor in connection with the performance and furnishing of the affected Work (except losses and damages within the deductible amounts of property insurance established by Owner in accordance with Article 5, provided they have resulted from causes other than the negligence of Contractor, any Subcontractor, or anyone directly or indirectly employed by any of them or for whose acts any of them may be liable).  Such losses shall include settlements made with the written consent and approval of Owner.  No such losses, damages and expenses shall be included in the Cost of the Work for the purpose of determining Contractor’s Fee.  If, however, any such loss or damage requires reconstruction and Contractor is placed in charge thereof, Contractor shall be paid for services a fee proportionate to that stated in Section 10.3.

.7	The cost of utilities, fuel and sanitary facilities at the site.

.8	Minor expenses such as telegrams, long distance telephone calls, telephone service at the site, expressage and similar petty cash items in connection with the Work.

.9	Cost of premiums for additional Bonds and Insurance required because of changes in the Work and premiums for property insurance coverage within the limits of the deductible amounts established by Owner in accordance with Article 5.

10.5	Excluded Costs.  The term Cost of the Work shall not include (i) expenses of Contractor's branch offices other than Contractor's office at the site, (ii) any part of Contractor’s capital expenses, including interest on Contractor's capital employed for the Work and charges against Contractor for delinquent payments (iii) cost of premiums for all Bonds and for all insurance whether or not Contractor is required by the Contract Documents to purchase and maintain same (except for cost of premiums covered by Subparagraph 10.4.5 above), (iv) costs due to the negligence of Contractor, any Subcontractor, or anyone directly or indirectly employed by any of them or for whose acts any of them may be liable, including, but not limited to, the correction of Defective Work, disposal of materials and equipment wrongly supplied and making good any damage to property, and/or (v) other overhead or general expense costs of any kind and the costs of any item not specifically and expressly included in Section 10.4.

10.6	Cash Allowances. It is understood that Contractor has included in the Contract Price all allowances so named in the Contract Documents, if any, and shall cause the Work so covered to be done by such Subcontractors or Suppliers and for such sums within the limit of the allowances as may be acceptable to Owner.  Contractor further agrees that:

10.6.1	The Cash Allowances include the cost to Contractor (less any applicable trade discounts) of materials and equipment required by the allowances to be delivered at the site and all applicable taxes; and

10.6.2	Contractor’s costs for unloading and handling on the site, labor, installation costs, overhead, profit and other expenses contemplated for the Cash Allowances have been included in the Contract Price and not in the Cash Allowances.  No demand for additional payment on account of any such costs will be valid.

10.6.3	Prior to final payment, an appropriate Change Order will be issued as recommended by Engineer to reflect actual amounts due Contractor on account of Work covered by Cash Allowances, and the Contract Price shall be adjusted accordingly.

## 10.7	Unit Price Work.

10.7.1. Where the Contract Documents provide that all or part of the Work is to be Unit Price Work, initially the Contract Price will be deemed to include for all Unit Price Work an amount equal to the sum of the established unit price for each separately identified item of Unit Price Work times the estimated quantity of each item as indicated in the Agreement.

10.7.2 The estimated quantities of items of Unit Price Work are not guaranteed and are solely for the purpose of comparison of Bids and determining an initial Contract Price. Determinations of the actual quantities and classifications of Unit Price Work performed by Contractor will be made by Engineer in accordance with paragraph 10.7.

10.7.3	Each unit price will be deemed to include an amount considered by Contractor to be adequate to cover Contractor's overhead and profit for each separately identified item.

10.7.4 The unit price of an item of Unit Price Work shall be subject to reevaluation and adjustment under the following conditions:

i.	If the total cost of a particular item of Unit Price Work amounts to five percent (5%) or more of the Contract Price and the variation in the quantity of that particular item of Unit Price Work performed by Contractor differs by more than twenty percent (20%) from the estimated quantity of such item indicated in the Agreement; and

ii.	If there is no corresponding adjustment with respect to any other item of Work; and

iii.	If Contractor believes that Contractor has incurred additional expense as a result thereof; or if Owner believes that the quantity variation entitles Owner to an adjustment in the unit price, either Owner or Contractor may make a claim for an adjustment in the Contract Price in accordance with Article 12 if the parties are unable to agree as to the effect of and such variation in the quantity of Unit Price Work performed.

ARTICLE 11 - CHANGE OF CONTRACT TIME; LIQUIDATED DAMAGES; DELAYS
AND HINDRANCES

11.1	Liquidated Damages - Assessment.  If Contractor does not achieve Substantial Completion or Final Completion of all elements of the Work within the time required by the Contract Documents, and liquidated damages are established by the Agreement or other Contract Documents to be assessed and recovered by Owner to compensate Owner for such delay in completion, it is understood and agreed that Owner will incur substantial damages and losses which are and will hereafter be difficult or impossible to quantify, ascertain and prove as actual damages for such delay.  Such damages are foreseen to include, without limitation, extended or additional costs for observation, inspection, engineering, utilities, insurance, administration, and also indeterminate damages, hindrance, or inconvenience to members of the public, deprivation of use and operation and impairment of financing.  Accordingly, and in lieu of actual damages, Contractor and his Surety shall be liable to Owner, and Owner shall be entitled to collect and recover such liquidated damages from Contractor and his Surety, in lieu of actual damages and not as a penalty, in the respective amounts per day for each calendar day that Substantial Completion or Final Completion of the entire Work, as appropriate, is delayed beyond the date(s) or time limitation(s) provided by the Contract Documents.  Neither partial acceptance nor partial Beneficial Occupancy or use of portions of the Work by Owner prior to achievement of Substantial Completion of all elements of the Work shall defeat or impair Owner's rights in respect to liquidated damages as provided by this Article.

11.2	Liquidated Damages - Reasonable Amount.  The original Contract Price provided in the Contract Documents shall be deemed to include adequate consideration and payment to compensate Contractor for the risk of liability imposed upon Contractor under this Section in respect to liquidated damages and Contractor acknowledges and agrees that the respective amounts of such liquidated damages are reasonable with due consideration for the type, nature and extent of the Work and the Contract Price and that such liquidated damages fairly approximate the nature and amount of actual damages which Owner may incur as a result of delayed completion and that such liquidated damages may be assessed and recovered by Owner without proof or evidence concerning the types or amounts of such actual damages.

11.3	Delay Following Termination.  The liquidated damages provided by this Article shall apply equally to delay in the achievement of Substantial Completion following abandonment of the Work by Contractor or termination by Owner because of Contractor's default, to the extent that such delays are caused in whole or in part by such abandonment, termination, default or other acts or omissions for which Contractor is responsible.  No delay or forbearance by Owner in enforcing any rights or remedies under the Contract Documents, including without limitation, the right to termination of the Contractor's right to proceed and the right to engage completion contractors to complete the Work shall constitute a waiver by Owner or deprive Owner of its right to retain, receive and recover such liquidated damages from Contractor and its surety or diminish the period of delayed completion from which such liquidated damages are to be determined.

11.4	Extension of Contract Time.  If Contractor is delayed or hindered at any time in the progress of the Work by any act or neglect of Owner or Engineer, or by any employee of either, or by changes ordered in the Work, or by unavoidable labor disputes, fire, unusual delay in transportation, unavoidable casualties, unforeseeable abnormal and unusually severe weather conditions, or any other causes beyond Contractor’s control and the risks of which are not otherwise assumed by Contractor under the Contract Documents (collectively referred to as Excusable Delays), or by delay authorized by Owner pending arbitration, or by any other cause which Owner, in consultation with Engineer, determines may justify the delay, then the Contract Time shall be extended by Change Order for such reasonable time as Owner may determine.  Contractor shall not be entitled to an extension of time for delays or hindrances caused by weather conditions or other natural phenomena of normal intensity for the locality and season during which Work is performed, unsuitable ground conditions except as may be provided in Article 4, inadequate construction forces, financial difficulties of Contractor or his Subcontractors or the failure of Contractor or its subcontractors or material suppliers to provide shop drawings or other required submittals on a timely basis and as scheduled or to place orders for equipment or materials sufficiently in advance to insure timely and proper delivery.

11.5	Notice of Delays or Hindrances. The Contract Time (or Milestones) may only be changed by a Change Order or by a Written Agreement.  Any claim for adjustment of the Contract Time (or Milestones) shall be based on written notice delivered by the party making the claim to the other party and to the Engineer promptly (but in no event later than twenty (20) days after the event or  occurrence of the event giving rise to the claim and stating the general nature of the claim.  Notice of the extent of the claim with supporting data shall be delivered within thirty (30) days after such occurrence or event giving rise to the claim (unless Engineer allows an additional period of time o ascertain more accurate data in support of the claim).  A notice of time extension request by Contractor under this Section shall be conclusively presumed to include all direct, indirect and cumulative impact upon the time required by Contractor to perform and complete the Work as a result of all facts, occurrences and events giving rise thereto.  Nothing provided in this Section shall be construed to afford the Contractor any rights or claims otherwise precluded by any other provisions of these General Conditions or other Contract Documents.

11.6	Time Extension As Exclusive Remedy.  As between Contractor and Owner, Contractor shall assume the risk of any and all suspensions of, delays or interference’s in or hindrances to the performance of the Work, regardless of the length thereof or the party responsible there for and arising from any and all causes whatsoever, including, without limitation, those due to any acts or omissions of or interference by Owner, Engineer, other contractors or Subcontractors, except only to the extent that an extension of time may be due to Contractor as expressly provided for in this Article for such suspension, delay, interference or hindrance.  Contractor shall bear all direct or indirect costs, expenses and liabilities which he may incur in connection with such suspensions, delays, hindrances or interference’s and all such suspensions, delays, interference’s or hindrances, costs, expenses and liabilities of any nature whatsoever, whether or not specifically described or referred to in the Contract Documents, shall conclusively be deemed to have been within the contemplation of the parties.

11.7	Limitations on Time Extensions.  Contract Time extensions will be granted only to the extent that Excusable Delays occur without concurrent non-excusable delays and actually extend the time required by Contractor to perform and complete critical Work elements and activities and which thereby cause an actual delay to achievement of Project completion.  Extensions of Contract Time shall be based solely upon the effect of delays to the Work as a whole.  The Contract Time shall not be extended for delays to parts of the Work, whether or not changed by any Change Order, that are not on the critical path of the progress schedule.  Concurrent Work activities, which are not critical to Project completion shall not be the subject of additional time extensions or compensation if those work activities are performed, or could be performed, within a moveable time frame concurrent with a critical item.

ARTICLE 12 - WARRANTIES, TESTS AND DEFECTIVE WORK

12.1	Warranty.  Contractor warrants and guarantees to Owner and Engineer that all Work will be performed, supplied, furnished and installed, and that the Work will be performed in strict accordance with the Contract Documents and will not be Defective.  Notice of all Work determined or suspected to be Defective or not in conformity with the Contract Documents shall be given to Contractor within a reasonable time after observance thereof.

12.2	Access to Work. Owner, Engineer and their respective representatives, and all governmental agencies with jurisdictional interests in respect of the Work or the activities of Contractor or its subcontractors shall be afforded complete and unhindered access to the Work for their observation, inspecting and testing.  Contractor shall provide proper and safe conditions for such access and advise them of Contractor’s site safety procedures and programs so that they may comply therewith as applicable.

12.3	Tests and Inspections.  Contractor shall give Engineer timely notice of readiness of the Work for all required inspections, tests or approvals.  If Laws or Regulations of any public body having jurisdiction require any Work (or part thereof) to specifically be inspected, tested or approved, Contractor shall assume full responsibility therefore, pay all costs in connection therewith and furnish Engineer the required certificates of inspection, testing or approval.  Contractor shall also be responsible for and shall pay all costs in connection with Owner’s or Engineer's acceptance of materials or equipment proposed to be incorporated in the Work, or of materials or equipment submitted for approval prior to Contractor's purchase thereof for incorporation in the Work.  The cost of all other inspections, tests and approvals which are required by Contract Documents shall be paid by Owner except as otherwise specified.  All inspections, tests or approvals other than those required by Laws or Regulations of any public body having jurisdiction shall be performed by organizations acceptable to Owner and Contractor or by Engineer if so specified.  Neither observations by Engineer nor inspections, tests or approvals by others shall relieve Contractor from Contractor's obligations to perform the Work in accordance with the Contract Documents.

12.4	Uncovering Work.  If any Work is covered contrary to written request of Engineer, it must, if requested by Engineer, be uncovered for Engineer's observation and replaced at Contractor’s expense.  If any Work (including the work of others) that is to be inspected, tested or approved is covered or reasonable access thereto is impaired without written concurrence of Engineer, it must, if requested by Owner or Engineer, be uncovered or access thereto open for observation.  Such uncovering shall be at Contractor’s expense unless Contractor has given Engineer timely notice of Contractor’s intention to cover such Work and Engineer has not acted with reasonable promptness in response to such notice.  If Engineer considers it necessary or advisable that covered Work be observed by Engineer or inspected or tested by others, Contractor, at Engineer’s request, shall uncover, expose or otherwise make available for observation, inspection or testing as Engineer may require, that portion of the Work in question, furnishing all necessary labor, material and equipment.  If it is found that such Work is Defective, Contractor shall bear all direct, indirect and consequential costs of such uncovering, exposure, observation, inspection and testing and of satisfactory reconstruction, (including, but not limited to, fees and charges of engineers, architects, attorneys and other professionals) and Owner shall be entitled to an appropriate decrease in the Contract Price by Change Order or Written Agreement.  If, however, such Work is not found to be Defective, Contractor shall be allowed an increase in the Contract Price or an extension of the Contract Time, or both, directly attributable to such uncovering, exposure, observation, inspection, testing and reconstruction; and, if the parties are unable to agree as to the amount or extent thereof, Contractor may make a claim therefore as provided in Articles 10 and 11.

12.5	Owner May Stop the Work.  If the Work is determined by Owner or Engineer to be Defective, or Contractor fails to supply sufficient skilled workers or suitable materials or equipment, or fails to furnish or perform the Work in such a way that the completed Work will conform to the Contract Documents, Owner may order Contractor to stop the Work, or any portion thereof, until the cause for such order has been eliminated; however, this right of Owner to stop the Work shall not give rise to any duty on the part of Owner to exercise this right for the benefit of Contractor or any other party.

12.6	Pre-Completion Correction or Removal of Defective Work.  If required by Owner or Engineer prior to Substantial Completion, Contractor shall promptly, as directed, either correct all Defective Work, whether or not fabricated, installed or completed, or, if the Work has been rejected by Owner or Engineer, remove it from the site and replace it with non-Defective Work.  Contractor shall bear all direct and consequential costs of such correction or removal, made necessary thereby, including but not limited to fees and charges of engineers, architects, attorneys and other professionals.

12.7	Post-Completion Correction Period.  Except as otherwise required by the Contract Documents or provided by any special warranties furnished there under, Contractor shall promptly and properly repair, replace, restore or rebuild, as Owner determines, any finished Work in respect of which defects of materials or workmanship may appear or as to which damage may occur because of such defects during the following periods: (i) for defects in materials, a period of three (3) calendar years commencing on the date of Substantial Completion, and (ii) for defects in workmanship, a period of three (3) calendar years commencing on the date of Final Acceptance.

12.7.1	In circumstances where Owner determines that a defect does not involve an imminent threat to persons, property or Owner’s ability to comply with governmental orders, laws or regulations, Owner shall give Contractor written notice of such defect.  Contractor shall, at its sole cost and within seven (7) calendar days after receipt of Owner’s written notice, commence the repair, replacement, restoration or rebuilding of the damaged or Defective Work using his own personnel or those of a third party, and shall diligently and without interruption complete all such required corrective action within a reasonable time.

12.7.2	In circumstances where Owner determines that a defect does involve an imminent threat to persons, property or Owners ability to comply with governmental orders, laws or regulations, Owner may, without notice to Contractor, immediately take such action as Owner deems necessary to effectuate the repair, replacement, restoration or rebuilding of any damaged or Defective Work or the protection and preservation of other Work or property threatened thereby.  As soon as practicable thereafter, Owner shall notify or otherwise afford Contractor a reasonable opportunity to investigate and continue or complete corrective action as required, if any.  If Contractor fails to commence and continue required corrective action in a prompt and timely manner, Owner may complete the repair, replacement, restoration or rebuilding of the damaged or Defective Work using its own personnel or those of a third party.

12.7.3	In all circumstances, Contractor and its surety shall be liable for any and all costs and damages sustained by Owner in respect of any such defect.

12.7.4	Nothing contained in this Section shall be construed to establish a period of limitation with respect to other obligations of Contractor under the Contract Documents, including, without limitation, Contractor's obligations under Warranties. Establishment of time periods in this Section relates only to the specific obligation of Contractor to correct the Work and has no relationship to the time within which proceedings may be commenced to establish or enforce Contractor’s liability with respect to obligations other than specifically to correct defects in the Work as prescribed by this Section.

12.7.5 If Contractor does not promptly comply with the terms of such instructions, or in an emergency where delay would cause serious risk of loss or damage, Owner may have the defective Work corrected or the rejected Work removed and replaced, and all claims, costs, losses and damages caused by or resulting from such removal and replacement (including but not limited to all costs of repair or replacement of work of others and attorneys’ fees) will be paid by Contractor.

12.7.6 Where defective Work (and damage to other Work resulting therefrom) has been corrected, removed or replaced under this paragraph 13.7, the correction period hereunder with respect to such Work will be extended for an additional period of one (1) year after such correction or removal and replacement has been satisfactorily completed.  If the defective work is completed or repaired in the third year.

12.8	Option To Accept Defective Work. Instead of requiring correction or removal and replacement of Defective Work, Owner (and, prior to Engineer’s recommendation of final payment) may elect to accept such Work in the condition as provided.  Contractor shall bear all direct, indirect and consequential costs attributable to Owner’s evaluation of and determination to accept such Defective Work, to include, but not be limited to, fees and charges of engineers, architects, attorneys and other professionals.  If any such acceptance occurs prior to Engineer's recommendation of final payment, a Change Order will be issued incorporating the necessary revisions in the Contract Documents with respect to the Work; and Owner shall be entitled to an appropriate decrease in the Contract Price to account for such costs and damages.  If the acceptance occurs after such recommendation of final payment, such costs and damages shall be paid by Contractor and its surety to Owner.

12.9	Owner May Correct Defective Work. If Contractor fails within seven (7) days after written notice from Engineer to correct Defective Work or to remove and replace rejected Work as provided by Section 12.6, or if Contractor fails in any respect to perform the Work in accordance with the Contract Documents or if Contractor fails to comply with any other provision of the Contract Documents, Owner may, after seven (7) days written notice to Contractor, correct and remedy any such deficiency, and may exclude Contractor from all or part of the site, take possession of all or part of the Work, suspend Contractor’s services related thereto, and take possession of Contractor’s tools, appliances, construction equipment and machinery at the site and incorporate in the Work all materials and equipment stored at the site or for which Owner has paid Contractor but which are stored elsewhere.  Contractor shall allow Owner, Engineer, their respective representatives and other contractors full and unhindered access to the site to enable Owner to exercise the rights and remedies under this Section.  All claims costs, losses and damages, including attorneys’ fees, incurred or sustained by Owner in exercising such rights and remedies will be charged against Contractor and a Change Order or Written Agreement will be issued incorporating the necessary revisions in the Contract Documents with respect to the Work.  Such direct, indirect and consequential costs shall include, but not be limited to, fees and charges of engineers, architects, attorneys and other professionals, all court and arbitration costs and all costs of repair and replacement of work or property of Owner or others destroyed or damaged by correction, removal or replacement of Contractor’s Defective Work Contractor shall not be allowed an extension of the Contract Time because of any delay or hindrance in performance of the Work. attributable to the exercise by Owner of Owner’s rights and remedies hereunder.

ARTICLE 13 - PAYMENTS TO CONTRACTOR AND COMPLETION

13.1	Schedule of Values.  Contractor shall provide Engineer with a Schedule of Values as required by Section 2.7.  The Schedule of Values will serve as a basis of progress payments during construction.

13.2	Basis For Payments.  Payment for the Work is based upon a lump sum and/or unit prices as established by the Agreement.  Subject to the limitations and conditions provided elsewhere in these General Conditions or in other Contract Documents, progress payments for lump sum items shall be based upon percentage of completion at the time of request for such payments as determined or approved by Engineer while progress payments for unit price Contract Items shall be determined by Engineer based upon approved estimated quantities of such items completed and in place.  The method for calculating estimated quantities shall be based upon reasonable engineering methods for such estimates.  If a unit price for a Contract Item includes compensation for successful testing of Work or for finish grading, cleanup or other surface or site restoration as part of such item, Owner may at its sole option deduct from payments and withhold (i) up to fifteen percent (15%) of the unit price for Work installed but not successfully tested, and (ii) up to ten percent (10%) of the unit price for Work installed but as to which finish grading, cleanup or other surface or site restoration has not been completed which sums shall be in addition to retainage and other amounts withheld by Owner as permitted by the Contract Documents.  Such sums shall be released to Contractor upon satisfactory completion of testing or restoration, as applicable.

13.3	Stored Materials and Equipment.  Payments for materials or equipment not incorporated into the Work, but delivered and suitably stored at the site, or, if provided by the Contract Documents or agreed upon in writing, at some other location off of the site, shall be conditioned upon compliance by Contractor with procedures satisfactory to Owner to establish Owner’s title to such materials and equipment or otherwise protect the Owner’s interest and shall include applicable insurance, storage and transportation to the site.  Payments for stored materials or equipment may not exceed one hundred percent (100%) less retainage of the net value of such stored material or equipment.

13.4	Specially Manufactured Items.  If payment for work on undelivered specifically manufactured items is permitted by the Contract Documents or by Owner’s written approval, such payment shall be conditioned upon submission by Contractor of bills of sale, invoices and other documentation establishing in favor of Owner a valid security interest in the items and establishing or certifying that the items are covered by appropriate Insurance and other arrangements to protect the Owner's interest therein, all of which will be satisfactory to Owner.  The Owner may further condition such payment upon Engineer’s observation of the progress of such items, and in such case Contractor shall provide transportation and reasonable lodging and other appropriate expenses for a representative of Owner or Engineer to travel to the place of manufacture of such equipment or material to conduct such observation.

13.5	Retainage.  Owner shall withhold retainage in the amount of ten percent (10%) of each Progress Payment until the Work or designated portion thereof is fifty percent (50%) complete.  Thereafter, no further retention under this Section shall be made, provided that Contractor is making satisfactory progress and there is no specific cause for greater withholding.  If required by governing statutes, such retainage shall be deposited into an interest bearing escrow account pursuant to the terms of a written Escrow Agreement executed in accordance with such statutes, and upon such form as approved by Owner.  Upon issuance and Owner's execution of a Certificate of Substantial Completion, Owner may reduce the retained amount to not less than two hundred percent (200%) of the cost of the Work remaining to be completed, corrected or accepted.  Retainage may not be reduced until Contractor provides Owner with complete and legally effective releases or waivers of all claims or liens arising out of or filed in connection with the Work, which instruments shall be upon such forms as approved by Owner.  In lieu thereof and as approved by Owner, Contractor may furnish receipts or releases in full; an affidavit of Contractor that the releases and receipts include all labor, services, material, and equipment for which a claim or lien could be filed, and that all payrolls, material work equipment bills, and other indebtedness connected with the Work for which Owner or his property might in any way be responsible have been paid or otherwise satisfied; and consent of the Surety, if any, to final payment.  If any Subcontractor, manufacturer, fabricator, supplier or distributor fails to furnish a release or receipt in full, Contractor may furnish a Bond or other collateral satisfactory to Owner to indemnify Owner against any claim or lien.

13.6	Applications for Progress Payment.  At least twenty (20) days before each Progress Payment is scheduled (but not more often than once a month), Contractor shall submit to Engineer for review a properly completed and signed Application for Payment upon such form as Owner may prescribe, together with such supporting documentation as Owner may prescribe under the Contract Documents.  The submission of any request for progress payment shall be deemed a waiver and release by Contractor of all liens and claims with respect to the Work and period to which such Progress Payment request pertains except as specifically reserved and noted on such request.  The second and each subsequent Application for Progress Payment shall include an affidavit from Contractor stating that all previous Progress Payments received on account of the Work have been applied to discharge in full all of Contractor’s obligations in respect of Work covered by prior Applications.  Owner or Engineer may reject Contractor's Application for Progress Payment if Contractor fails to submit updated progress schedules as provided in Section 2.7.

13.7	Payroll Reports.  Contractor's Application for Payment shall be accompanied by a payroll report by Contractor and each of its Subcontractors for the pay period covered by the application.  The report shall state, as to each employee, his/her name, address and social security number, work classification, hours worked, rate of pay, itemized deductions, gross amount earned, net pay and fringe benefit information.  This report shall be provided either on Federal Form WH-347 for reporting prevailing wages under the Davis Bacon Act, or otherwise by submitting the payroll information in Contractor’s format along with Federal Form WH-348 Statement of Compliance under the Davis Bacon Act.

13.8	Contractor’s Warranty of  Title.  Contractor warrants and guarantees that title to all Work, materials and equipment covered by any Application for Payment, whether incorporated in the project or not, will pass to Owner no later than the time of payment free and clear of all claims and liens.

13.9	Action Upon Applications for Payment. Engineer will, within five (5) days after receipt of each Application for Payment, either (i) indicate in writing a recommendation of payment and present the Application to Owner, or (ii) return the Application to Contractor indicating in writing Engineer’s reasons for refusing to recommend payment.  In the latter case, Contractor may make the necessary corrections and resubmit the Application to Owner, with notice that the deficiencies noted by Engineer have been corrected.  Payments to Contractor shall not be due until the expiration of thirty-five (35) days from the date of Owner's approval of Engineer's recommendation of payment.  Engineer may refuse to recommend the whole or any part of any payment if, in Engineer’s opinion, it would be incorrect to make such representations to Owner.  Engineer may also refuse to recommend any such payment or, because of subsequently discovered evidence or the results of subsequent inspections or tests, nullify any such payment previously recommended, to such extent as may be necessary in Engineer's opinion to protect Owner from loss because (i) the Work is Defective, or completed Work has been damaged requiring correction or replacement, (ii) the Contract Price has been reduced by Written Amendment or Change Order, (iii) Owner has suffered a loss as provided in Section 6.24 or has been required to correct Defective Work or complete Work in accordance with Section 12.9, or (iv) of Engineer’s actual knowledge of the occurrence of any of the events enumerated in Sections 14.2. Owner may refuse to make payment of the full amount recommended by Engineer because claims have been made against Owner on account of  Contractor’s performance or furnishing of the Work, or claims have been filed in connection with the Work, or there are other items entitling Owner to a set-off against the amount recommended, but Owner must give Contractor immediate written notice (with a copy to Engineer) stating the reasons for such action.

13.10	Substantial Completion.  When Contractor considers the entire Work ready for its intended use Contractor shall, in writing to Owner and Engineer, request the issuance of a Certificate of Substantial Completion.  Within a reasonable time thereafter, Engineer shall respond to Contractor by either (a)	scheduling an inspection of the Work by Owner, Engineer and Contractor to determine the status of completion or (b) notifying Contractor in writing that the Work has been determined by Owner or Engineer not to be substantially complete and explaining the basis therefore.  If, after such inspection, Owner and Engineer conclude that the Work is not substantially complete, Engineer will, within fourteen (14) days after such inspection, notify Contractor in writing, stating basis therefore.  If, after the inspection, Owner and Engineer consider the Work substantially complete, Engineer shall prepare and deliver to Owner a recommended Certificate of Substantial Completion, which shall fix the date of Substantial Completion, and address the respective responsibilities of Owner and Contractor with respect to security, operation, safety, maintenance, heat, utilities, insurance and warranties.  The Certificate, as recommended by Engineer or as approved by Owner, may have attached a list of items to be completed or corrected prior to final payment and may state any additional issues or reservations to remain unaffected by substantial completion.  The certificate of Substantial Completion, as accepted and approved by Owner, will be submitted to Contractor for acceptance, which acceptance shall be deemed effective, and Contractor shall become unconditionally bound to the terms thereof, upon (i) Contractors execution of the certificate, or (ii) Contractor's failure to provide written notice objecting to the terms of such certificate within five (5) days after receipt thereof.

13.11	Site Access Upon Substantial Completion. Owner shall have the right, but not the obligation, to exclude Contractor from the site of the Work after the date of Substantial Completion, but Owner shall allow Contractor reasonable access to the site to complete or correct items of Work or to fulfill other obligations as provided by the Certificate of Substantial Completion.

13.12	Partial Utilization and Occupancy.  Use or occupancy by Owner of portions of the Work may be accomplished prior to Substantial Completion of all the Work upon determination by Owner in consultation with Engineer that any such portion constitutes a separately functioning and usable part of the Work that can be used by Owner without causing substantial interference with Contractor's performance of the remainder of the Work, subject to the following:

13.12.1	Owner, at any time may give written notice to Contractor of Owner’s intent to use or occupy any part of the Work, which Owner believes to be ready for its intended use and substantially complete.  If Contractor agrees, Contractor will certify to Owner and Engineer that said part of the Work is substantially complete and request Engineer to issue a Certificate of Partial Substantial Completion for that part of the Work.  Contractor, at any time, may notify Owner and Engineer in writing that Contractor considers any such part of the Work ready for its intended use and substantially complete and request Engineer to issue a Certificate of Partial Substantial Completion for that part of the Work.  The provisions and procedures set forth in Sections 13.10 and 13.11 shall govern inspections and recommendations concerning partial substantial completion and certification thereof.

13.12.2	Owner may, at any time, give written notice to Contractor of Owner's intent to use or occupy any part of the Work, which is not substantially complete.  Within a reasonable time thereafter Owner, Contractor and Engineer shall make an inspection of that part of the Work to determine its status of completion and shall prepare a list of the items remaining to be completed or corrected thereon before final payment.  Upon failure of the parties to agree upon such list, Engineer will promptly finalize the list and deliver same to Owner and Contractor together with a written determination as to the division of responsibilities pending final payment between Owner and Contractor with respect to security, operations, safety, maintenance, utilities, insurance, warranties and guarantees for that part of the Work.  Such list and determination will become binding upon Owner and Contractor except as otherwise agreed in writing between them.  During the period of Owner’s use or occupancy of such part of the Work, Owner shall afford Contractor reasonable access and opportunity to complete or correct items on said list and to complete other related Work.

13.12.3	No occupancy or separate operation of part of the Work will be accomplished prior to compliance with the requirements of Section 5.9 with respect to property insurance.

13.13	Final Inspection.  Upon written notice from Contractor that the entire Work or an agreed upon portion thereof is complete, Engineer will make a final inspection with Owner and Contractor and will notify Contractor in writing of all particulars in which this inspection reveals that the Work is incomplete or Defective.  Contractor shall immediately take such measures as are necessary to complete and remedy such Work to the satisfaction of Owner and Engineer.  Upon written notice from Contractor that all Work, which was incomplete or defective has been completed or remedied, Engineer and Owner will make an additional inspection to verify the work performed.  If it is determined that the Work is still incomplete or defective, Contractor shall bear all direct, indirect and consequential costs of re-inspecting said Work (including, but not limited to, fees and charges of engineers, architects, attorneys, and other professionals) and Owner shall be entitled to an appropriate decrease in the Contract Price by Change Order or written agreement.

13.14	Final Application for Payment.  After Contractor has completed the Work and all corrections as provided elsewhere in this Article and delivered all maintenance and operating instructions, schedules, guarantees, bonds, certificates of inspection, marked-up record documents (as provided in Section 6.19) and all other documents as required by the Contract Documents, and after Engineer has indicated that the Work is acceptable (subject to the provisions of Section 13.16), Contractor may make application for Final Payment which, except as otherwise provided in this Article, shall be subject to the procedures and requirements in respect of progress payments.  The Final Application for Payment shall be accompanied by complete and legally effective releases or waivers by all subcontractors and material suppliers from all claims or liens arising out of or filed or which could otherwise be filed in connection with the Work.  In lieu thereof and as approved by Owner, Contractor may furnish: receipts or releases in full; an affidavit from Contractor that the releases and receipts include all labor, services, material and equipment for which a claim or lien could be filed, and that all payrolls, material and equipment bills, and other indebtedness connected with the Work for which Owner, contract funds or Owner's property might in any way be responsible have been paid or otherwise satisfied; and consent of the Surety to final payment.  If any Subcontractor or Supplier fails to furnish a release or receipt in full, Contractor may, at Owner's option, furnish a Bond or other collateral satisfactory to indemnify Owner against any claim or lien.  Contractor's Application for Final Payment shall be accompanied by a list of all Subcontractors involved in the project, and the amount in dollars paid to each Subcontractor.  The list shall identify MBEs and WBEs and shall include the final Contract Price for each.

13.15	Final Payment and Acceptance.  If, on the basis of Engineer’s observation of the Work during construction and final inspection, and Engineer’s review of the Final Application for Payment and accompanying documentation, all as required by the Contract Documents, Owner is satisfied that the Work has been completed and Contractor’s other obligations under the Contract Documents have been fulfilled, Engineer will, within ten (10) days after receipt of the Final Application of Payment, indicate in writing Engineer’s recommendation of payment and present the Application to Owner for payment.  Otherwise, Engineer will return the Application to Contractor, indicating in writing the reasons for refusing to recommend Final Payment, in which case Contractor shall make the necessary corrections and resubmit the Application.  If the application and accompanying documentation are approved by Owner as to form and substance, Owner shall pay Contractor the amount recommended by Engineer.

13.16	Delayed Final Completion.  If, through no fault of Contractor, final completion of the Work is significantly delayed and if Engineer so confirms, Owner will, upon receipt of Contractor’s Final Application for Payment and recommendation of Engineer, and without terminating the Agreement, make payment of the balance due for that portion of the Work fully completed and accepted.  If the remaining balance to be held by Owner for Work not fully completed or corrected is less than the retainage stipulated in the Agreement, and if Bonds have been furnished as required in Section 5.1, the written consent of the Surety to the payment of the balance due for the portion of the Work fully completed and accepted shall be submitted by Contractor to Engineer with the Application for such payment.  Such payment will be made under the terms and conditions governing Final Payment, except that it shall not constitute a waiver of claims.

13.17	Contractor’s Continuing Obligations.  Except as otherwise expressly provided to the contrary by the Contract Documents, Contractor's duty to perform and complete the Work and to fulfill other obligations in accordance with the Contract Documents shall be absolute.  Neither recommendation of any Progress Payment or Final Payment by Engineer, nor approval or acceptance thereof by Owner, nor the issuance of a Certificate of Substantial Completion, nor any payment by Owner to Contractor under the Contract Documents, nor any use or occupancy of the Work or any part thereof by Owner, nor any act of acceptance by Owner nor any failure to do so, nor any review and approval of a Shop Drawing or sample submission, nor any activities by Contractor or Owner in correction of Defective Work will constitute an acceptance of Work not in accordance with the Contract Documents or a release or waiver of Contractor’s obligations under the Contract Documents or of Owner’s rights and remedies there under.

13.18	Waiver of Claims By Final Payment.  The making and acceptance of Final Payment shall constitute a waiver of all claims by Contractor against Owner except (i) claims previously made in writing by either party and remaining unsettled as of the date of final payment, (ii) claims by Owner attributable to Defective Work or prior corrective work, appearing after final inspection or from failure to comply with the Contract Documents, (iii) Owner claims and other rights arising under the terms of any general or special warranties or guarantees specified by the Contract Documents or arising there under, and (iv) Owner claims and other rights in respect of Contractor’s and its surety's continuing obligations under Laws and Regulations or the Contract Documents;

ARTICLE 14 - SUSPENSION OF WORK AND TERMINATION

14.1	Owner May Suspend Work. Owner may, at any time and without cause, suspend the Work or any portion thereof by notice in writing to Contractor and Engineer, which will fix either the date or requisite events for resumption of the Work.  Contractor shall resume the Work on the date so fixed.  Contractor may make a claim for an extension of the Contract Time on account of such suspension, as provided by and subject to the limitations of Article 11 hereinabove.

14.2	Contractor Default.  The Owner may declare Contractor to be in default under the Agreement and may terminate Contractor's right to proceed thereunder if Contractor (i) is adjudged a bankrupt or insolvent, or makes a general assignment for the benefit of creditors, or Contractor or a third party files a petition to take advantage of any debtors act or to reorganize under the bankruptcy or similar laws, or a trustee or receiver is appointed for Contractor or for any of Contractor's property on account of the Contractor’s insolvency, and Contractor or its successor in interest does not provide adequate assurance of future performance in accordance with the Contract Documents within ten (10) days of receipt of a written request by Owner for such assurance; or (ii) admits in writing an inability to pay his debts generally as they become due; or (iii) fails or refuses to perform or prosecute the Work or any separate part or element thereof in accordance with the Contract Documents and with such diligence as will insure its completion within the Contract time, or Contractor fails to complete the Work within such Contract Time; or (iv) performs any Work which is rejected as Defective and fails or neglects to correct any such Work, or (v) fails to supply sufficient skilled workers or suitable materials or equipment; or (vi) fails to adhere to the original and any revised progress schedules established under the Contract Documents; or (vii) fails to make prompt payment to laborers, subcontractors and material suppliers; or (viii) abandons or suspends performance of any of the Work, or removes from the site materials or equipment reasonably required to perform and complete the Work, without Owner's written consent, directive or approval; or (ix) disregards Laws or Regulations or similar requirements and orders of any public body having jurisdiction; or (x) disregards the authority of Owner or Engineer, or (xi) otherwise violates in any material way any provisions or requirements of the Contract Documents.

14.3	Default Termination By Owner.  Upon occurrence of any of the events of default provided by Section 14.2, Owner may, after giving Contractor and the Surety seven (7) days written notice, terminate the Agreement and Contractor's right to proceed there under, which termination shall become effective without further notice upon the expiration of such seven (7) day period, unless otherwise rescinded or modified by Owner in writing.  The following shall govern in the event of a default termination by Owner as provided by this Section:

14.3.1	Owner may exclude Contractor from the site and take possession of the Work and of all Contractor’s tools, appliances, construction equipment and machinery at the site and use or authorize third party contractors to use the same for completing or correcting the Work, and incorporate in the Work all materials and equipment stored at the site or for which Owner has paid Contractor but which are stored elsewhere.  Owner and completion contractors shall not be liable to Contractor for the cost or value of any such property used or incorporated in the course of such completion or correction;

14.3.2	Owner may, by any means it may deem expedient and appropriate under the circumstances, complete and correct or contract with one or more separate contractors for completion and correction of the Work.  Owner shall not be required to accept the lowest price or the shortest duration proposed for such completion or corrective Work.  In the event that Owner takes Bids for completion or corrective Work, Contractor shall not be eligible for the award of any contracts resulting there from.

14.3.3	Contractor shall not be entitled to receive any further payment until all Work is completed and corrected and the total costs incurred by Owner in respect of such completion and correction have been ascertained.

14.3.4	Contractor and its surety shall be liable for liquidated damages for delayed completion of the Work as provided in the Contract Documents, based upon (i) the agreed dates for substantial and final completion as established by the contract(s) between Owner and the completion contractors, or (ii) the actual dates of substantial and final completion, whichever occurs first;

14.3.5	If the unpaid balance of the Contract Price exceeds the sum of (i) liquidated damages (ii) the Completion Costs as herein defined, (iii) such other damages to which Owner is entitled by reason of Contractor's breach or default under the Agreement or the termination thereof, and (iv) attorney fees incurred by Owner incidental to the enforcement of any rights and remedies against Contractor and its Surety afforded by the Contract Documents, such excess will be paid to Contractor or Surety as appropriate.  If such sum exceeds such unpaid balance, Contractor and its surety shall pay the difference to Owner.

14.3.6	As used in this Section, the term “Completion Costs” shall mean any and all direct, indirect and consequential costs and expenses paid or incurred by Owner for or incidental to completion of the Work or correction of previous Work performed by Contractor, whether by Owner’s own forces or by one or more separate contractors engaged by Owner for such purposes, and shall include but not be limited to all fees and charges of engineers, architects, consultants, attorneys and other professionals, plus court costs, arbitration and arbitrator fees and charges.

14.3.7	Termination will not affect any rights or remedies of Owner against Contractor then existing or which may thereafter accrue.  Any retention or payment of moneys due Contractor by Owner will not release Contractor from liability.

14.3.8	If it is determined for any reason that Contractor was not in default, the termination shall be deemed a termination for convenience of the Owner, whereupon the rights and obligations of the parties shall be determined and governed in accordance with Section 14.4.

14.4	Termination For Convenience.  Upon seven (7) days' written notice to Contractor and Engineer, Owner may, without cause and without prejudice to any other right or remedy of Owner, elect to terminate the Agreement in whole or in part for its convenience.  Contractor shall immediately discontinue Work and follow all other instructions of Owner as stated in such notice, and shall take all other action as may be required or appropriate to minimize costs, damages and expenses in consequence of the termination.  Furthermore, Contractor shall deliver to Owner all survey notes, drawings, specifications and estimates completed or partially completed and these shall become the property of Owner.  Contractor shall not be entitled to payment on account of loss of anticipated profits or revenue or other economic loss associated with any terminated Work.   Amounts payable to Contractor shall be limited to the following:

14.4.1	A portion of the Contract Price as fairly allocated to Work executed by Contractor in accordance with the Contract Documents prior to the effective date of termination;

14.4.2	Reasonable expenses sustained by Contractor prior to the effective date of termination in performing services and furnishing labor, materials or equipment as required by the Contract Documents in connection with uncompleted Work, plus fair and reasonable sums for overhead and profit on such expenses, which shall not exceed the percentages established in Article 10;

14.4.3	Reasonable costs, losses and damages paid by Contractor in settlement of just claims under terminated contracts with Subcontractors, Suppliers and others.

14.5	Contractor Suspension of Work and Right To Terminate.  If, through no act or fault of Contractor, the Work is suspended for a period of more than ninety (90) days by Owner or under an order of court or other public authority, or Owner substantially fails to perform or make payment to Contractor as prescribed by the Contract Documents, Contractor may, upon thirty (30) days written notice to Owner and Engineer, terminate the Agreement and recover from Owner payment for all Work executed and any expense sustained plus reasonable termination expenses.

ARTICLE 15 - MISCELLANEOUS

15.1	Giving Notice. Whenever any provision of the Contract Documents requires the giving of written notice, it will be deemed to have been validly given if delivered in person or by facsimile telephone transmission (FAX) to the individual or to a member of the firm or to an officer of the corporation for whom it is intended, or if sent by registered or certified mail, postage prepaid, to the last business address known to the giver of the notice.

15.2	Computation of Time. When any period of time is referred to in the Contract Documents by days, it shall be computed to exclude the first and include the last day of such period.  If the last day of any such period falls on a Saturday or Sunday or on a day made a legal holiday by the law of the applicable jurisdiction such day shall be omitted from the computation.  A “day” and a "calendar day” are defined as twenty-four hours measured from midnight to the next midnight.

15.3	Injury to Persons and Property.  Should Owner or Contractor suffer injury or damage to his person or property because of any error, omission or act of the other party or of any of the other party’s employees or agents or others for whose acts the other party is legally liable, claim will be made in writing to the other party within a reasonable time of the first observance of such injury or damage.  The provisions of this Section shall not be construed as a substitute for or a waiver of the provisions of any applicable statute of limitations or repose.

15.4	Cumulative Duties and Rights.  The duties and obligations imposed by these General Conditions and the rights and remedies available hereunder to the parties hereto are in addition to, and not to be construed in any way as a limitation of any rights and remedies available by Laws and Regulations, by special warranty or guarantee or by other provisions of the Contract Documents, and the provisions of this Section shall be as effective as if repeated specifically in the Contract Documents in connection with each particular duty, obligation, right and remedy to which they apply.

15.5	Assignment.  Except as provided for in Section 6.8, Contractor may not delegate his duty of performance or assign all or part of his obligations or rights under the Contract Documents without Owner’s prior written consent.  Subject to the restrictions of the preceding sentence, the Contract Documents are binding upon Owner and Contractor, their successors or assigns.

15.6	Governing Law.  The Contract Documents shall be interpreted in accord with and governed by the laws of the State of Indiana, except for the conflict of laws provisions thereof.   If any provision of the Contract Documents is found to be in conflict with those laws, the remaining provisions of the Contract Documents shall remain in effect.  Owner and Contractor agree that any litigation associated with or arising from the Agreement shall be filed with a court of competent jurisdiction within Hamilton County, Indiana.

15.7	Indiana Department of Transportation Standard Specifications.  All applicable portions of the Indiana Department of Transportation (INDOT) Standard Specifications shall apply to these Contract Documents to the extent not in conflict with the terms thereof.  Where the words 'Standard Specifications' along with a reference consisting of a number or number and letter are used, they shall be construed as referring to the Indiana Department of Transportation Standard Specifications and the most recent supplemental specifications issued prior to Bid opening.

15.8	Salvage of Existing Equipment and Materials.  Unless otherwise provided all existing equipment and materials as listed in the Technical Specifications, removed from existing facilities shall remain the property of Owner.  Such equipment and materials shall be stored on-site at locations identified by Engineer.  All other existing equipment and materials removed from existing facilities shall be the property of Contractor and shall be removed from the site.

15.9	English Language Requirement.  All submittals, including, but not limited to, all shop drawings, catalog cuts, manufacturers' recommendations, and assembly and maintenance instructions shall only be written in the English language.

15.10	Trade Practice.  In the event of any inconsistencies between the requirements of the Contract Documents and normal practice in the trade, the requirements of the Contract Documents shall control.

15.11	Cross-References.  Cross-references in the Contract Documents are not intended as complete lists of related requirements specified elsewhere.  The absence of a cross-reference to another section of the Contract Documents should not be deemed or construed to indicate that such other section does not specify related requirements where the two sections, read together, indicate otherwise.

15.12	Accounting Records. Contractor shall maintain proper accounting records for the work to be performed under this Agreement and shall provide an accounting for all charges and expenditures as may be necessary for auditing purposes.  All such records shall be subject to examination and inspection by Owner representatives at reasonable hours.

15.13	Steel Products.  In accordance with Indiana Code 5-16-8, if steel products are to be utilized or supplied in the performance of any contract or subcontract, only domestic steel products shall be used.  Reference is hereby made to such statute for definitions applicable to this Section.  Owner may not authorize or make any payment to Contractor unless Owner is satisfied that Contractor has fully complied with this provision.

15.14	Non-Discrimination. Contractor certifies for itself and all its subcontractors compliance with all existing laws of the United States and the State of Indiana prohibiting the discrimination against any employee or applicant for employment or subcontract work in the performance of the Work contemplated by the Agreement with respect to hire, tenure, terms, conditions or privileges of employment or any matter directly or indirectly related to employment or subcontracting because of race, religion, color, sex, handicap, national origin, ancestry, age, disabled veteran status or Vietnam era veteran status.  The City of Carmel reserves the right to collect a penalty as provided in IC 5-16-6-1 for any person discriminated against.

15.15	Operating Instructions.  Contractor, through qualified individuals, shall adequately instruct designated employees of the Owner in the operation and care of all equipment installed hereunder, except for equipment that may be furnished by the Owner.  Contractor shall also furnish and deliver to Engineer within forty-five (45) days of the shop drawing approval date, five (5) complete sets for permanent files, identified in accordance with the section hereof headed “Working Drawings”, of instructions, technical bulletins and any other printed matter, such as diagrams, prints or drawings, containing full information required for the proper operation, maintenance and repair of the equipment installed and the ordering of spare parts, except for equipment that may be furnished by Owner.

15.16	Operation and Maintenance Manual.  Contractor shall prepare and submit to Engineer five (5) copies of an Operation and Maintenance (O&M) Manual for all equipment and associated control systems furnished and installed under this Contract, if applicable.  When the Work reaches sixty-five (65) to seventy (70) percent completion Contractor shall submit to Engineer for approval two (2) copies of the manual with all specified material that is available at that time.  The submittal shall accompany Contractor’s partial payment request for the specified completion.  Within thirty (30) days after Engineer's approval of the two-copy submittal Contractor shall furnish to Engineer the five (5) copies of the manual.  Appropriate space shall be left in the manual for material not available at the time of submittal.  All missing material for the manual shall be submitted prior to the request for final payment.

15.16.1	Each copy of the manual shall be prepared and arranged as follows:

1.	One copy of each manufacturer's operation, lubrication and maintenance instructions and spare parts list for all equipment and controls furnished.  All equipment operating, lubrication and maintenance instructions and procedures and parts lists shall be furnished on 8 1/2 x 11 inch commercially printed or typed forms.  Such forms shall include equipment name, serial number and other identifying references.

2.	List of electrical relay settings and control and alarm contact settings.

3.	Electrical interconnection wiring diagram for equipment furnished including all control and lighting systems.

15.16.2	Each copy of the manual shall be assembled in one or more binders, each with the title page, typed table of contents, and heavy section dividers with copper reinforced holes and numbered plastic index tabs.  Each manual shall be divided into sections paralleling the “Workmanship and Materials” equipment specifications.  Binders shall be 3-ring, hard-back Type No. S-43772 as manufactured by Marshall-Jackson Co, Chicago, Illinois, or equal.  All loose data shall be punched for binding and composition and printing shall be arranged so that punching does not obliterate any data.  The cover and binding edge of each manual shall have the project title and manual title printed thereon, all as furnished and approved by Engineer.

15.16.3	All operating and maintenance material that comes bound by the equipment manufacturer shall be left that way.  The appropriate sections of Contractor's O&M Manual shall cross-reference the manufacturers bound manual.

15.16.4	Where more than one (1) binder is required they shall be labeled Vol. 1, Vol. 2, and so on.  The table of contents for the entire set, identified by volume number, shall appear in each binder.

15.16.5	The five (5) copies of the manuals and data included therein shall be provided in conformance with the subsection headed "Working Drawings" and, in addition, to the requirements of the Technical Specifications Workmanship and Materials Section.  The costs of the Operation and Maintenance Manual shall be included in the lump sum Contract Price and no separate payment will be made therefore.  The Operation and Maintenance Manual shall be included as a separate item in Contractor's schedule of values.

15.17	Service of Manufacturer’s Representatives.  The Contract Price shall include the costs of furnishing competent and experienced engineers, superintendents or other technically qualified representatives who shall represent equipment manufacturers and shall assist Contractor, when required, to install, adjust, test and place in operation equipment in conformity with the Contract Documents.  When equipment is ready for permanent operation, such engineers, superintendents or representatives shall make all adjustments and tests required by Engineer to prove that such equipment is in proper and satisfactory operating condition, and shall instruct such personnel as may be designated by Owner in the proper operation and maintenance of such equipment.

15.18	Water. Contractor shall provide, at its expense, the necessary water supply for Contractor's activities, and shall, if necessary, provide and lay necessary water lines from existing mains to the place where such water service is required, and shall secure all necessary permits and pay for all hookups, meters and taps to water mains or hydrants and for all water used at the established rates.

15.19	Light and Power. Contractor shall provide, at its own expense, temporary lighting and power facilities required for the proper prosecution and inspection of the Work, unless specified otherwise.  Contractor shall meter and pay for Contractor’s share of all power utilized.

15.20	Contractor’s Field Office. Contractor shall erect, furnish and maintain a field office with a telephone at the site during the entire period of construction.  He or an authorized agent shall be present at this office at all times while his work is in progress.  Readily accessible copies of both the Contract Documents and the latest approved Working Drawings shall be kept at this field office.

15.21	Prevention, Control and Abatement of Erosion and Water Pollution. Contractor shall be responsible for prevention, control and abatement of erosion, siltation and water pollution resulting from construction of the project until Final Acceptance of the project.

15.21.1	Contractor shall provide, install, construct and maintain coverings, mulching, sodding, sand bagging, berms, slope drains, sedimentation structures or other devices necessary to meet Owner, State and Federal regulatory agency codes, rules and laws.

15.21.2	Contractor shall take sufficient precautions to prevent pollution of adjacent rivers and streams with fuels, oils, bitumens, or other harmful materials.  Also, Contractor shall conduct and schedule operations so as to avoid or otherwise minimize pollution or siltation of the waters.

15.21.3	Storm drainage facilities, both open and closed conduit, serving the construction site shall be protected by the Contractor from pollutants and contaminants.  If it is determined that siltation of drainage facilities has resulted due to the project, Engineer will advise Contractor to remove and properly dispose of the deposited material.  Should Contractor fail to or elect not to remove the deposits, Owner will provide maintenance cleaning as needed and will charge all costs of such service against the amount of money due or to become due Contractor.

15.21.4	Excavated material shall not be deposited in streams, ditches or impoundments, or in a position close enough thereto to be washed away by high water or runoff.

15.21.5	Contractor shall not disturb lands or waters outside the limits of construction and public rights of way.  The location of and methods of operation in all detention areas, borrow pits, material supply pits and disposal areas furnished by Contractor shall meet the approval of Engineer as being such that erosion during and after completion of the Work will not likely result in detrimental siltation or water pollution.

15.21.6	Contractor shall schedule operations such that the area of unprotected erodible earth exposed at any one time is not larger than the minimum area necessary for efficient construction operations; and the duration of exposure of uncompleted construction to the elements shall be as short as practicable.

15.21.7	Clearing and grubbing shall be so scheduled and performed that grading operations can follow immediately thereafter, and grading operations shall be so scheduled and performed that permanent erosion control features can follow immediately thereafter if conditions on the project permit.

15.21.8	The surface areas of unprotected erodible earth exposed by clearing and grubbing, excavation or filling operations shall be kept to a minimum.  Immediate erosion or pollution control measures to prevent siltation or contamination of any stream, ditch or other impoundment or to prevent damage to the project or property outside the project limits shall be provided when necessary.

15.22	Air Borne Particulate.  Contractor shall comply with Indianapolis Air Pollution Regulation II-4, which is hereby incorporated into this Section by reference.  A copy of such regulation will be furnished to Contractor upon request.

15.23	Professional Fees and Court Costs Included.  Whenever reference is made to claims, costs, losses or damages recoverable by Owner against Contractor or its surety, such recovery shall include, but not be limited to, all fees and charges of engineers, architects, attorneys and other professionals and all court or arbitration or other dispute resolution costs.

END OF THIS SECTION